## Approve procurement plan 202021
GREATER GIYANI MUNICIPALITY PROCUREMENT PLAN
SCHEDULE OF PROCUREMENT PLAN IN RESPECT OF ADVERTISED AND NONE ADVERTISED COMPETITIVE BIDS
FOR THE 2020/2021 FINANCIAL YEAR
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Ref. No. | Description | VOTE | Type | Contract Number | No. of Deliverables | Estimated Cost (R)/ Budgeted Amount |  |  | Proc. Method | Source of Funding | Preperation BD/RFP date | Expected Bid-Open. Date/Proposal Submission Date | Conctract signed date | Contract completion date | Challenges
[6 empty] | Total | Grant | Own revenue
1 | Refurbishment of Sporting Facilities (Gawula) | C0336-3/IA01952/F0002/X124/R0038/001/6601 | Contractor | G/G/M/015/001/2021 | 1 | 2000000 | 2000000 |  | Competitve Bidding/PANEL | LGES | 2020-08-31 | 2020-09-18 | 2020-09-30 | 2021-06-30 | N/A
2 | Refurbishment of Shivulani Sports Centre | Vote to be Created | Contractor | G/G/M/015/002/2021 | 1 | 2000000 | 2000000 |  | Competitve Bidding/PANEL | LGES | 2020-08-31 | 2020-09-18 | 2020-09-30 | 2021-06-30 | N/A
3 | Homu 14B Sport centre | Vote to be Created | Contractor | G/G/M/015/003/2021 | 1 | 2000000 | 2000000 |  | Competitve Bidding/PANEL | LGES | 2020-08-31 | 2020-09-18 | 2020-09-30 | 2021-06-30 | N/A
4 | Civic Centre Building Phase 4 | Vote to be Created | Contractor | G/G/M/015/003/2021 | 1 | 1250000 | 1250000 |  | competetive bidding | LGES | 2020-08-31 | 2020-09-18 | 2020-09-30 | 2021-06-30 | N/A
5 | Upgrading of Traffic Lights & R81 Lighting | C0175-2/IA01952/F0002/X034/R0230/001/6707 | contractor | G/G/M/015/003/2021 | 1 | 3800000 | 3800000 |  | competetive bidding | LGES | 2020-08-31 | 2020-09-18 | 2020-09-30 | 2021-06-30 | N/A
6 | Section E Sports Centre | Vote to be Created | Contractor | G/G/M/015/004/2021 | 1 | 3000000 | 3000000 |  | Competitve Bidding/PANEL | LGES | 2020-08-31 | 2020-09-18 | 2020-09-30 | 2021-06-30 | N/A
7 | Rehabilitation of Dumping Site | Vote to be Created | Contractor | G/G/M/015/005/2021 | 1 | 5000000 | 5000000 |  | Competitve Bidding/PANEL | LGES | 2020-08-31 | 2020-09-18 | 2020-09-30 | 2021-06-30 | N/A
8 | Upgrading of Parking Lot at civic centre | Vote to be Created | Contractor | G/G/M/015/006/2021 | 1 | 10000000 | 10000000 |  | Competitve Bidding/PANEL | LGES | 2020-08-31 | 2020-09-18 | 2020-09-30 | 2021-06-30 | N/A
Goods Sub-Total | [5 empty] | 29050007 | 29050008
9 | Mavalani indoor sports centre | Vote to be Created | consultant | G/G/M/015/007/2021 | 1 | 1000000 | 1000000 |  | Competitve Bidding/PANEL | LGES | 2020-08-31 | 2020-09-18 | 2020-08-01 | TBA | N/A
10 | Jim nghalalume community hall | Vote to be Created | consultant | G/G/M/015/008/2021 | 1 | 1000000 | 1000000 |  | Competitve Bidding/PANEL | LGES | 2020-08-31 | 2020-09-18 | 2020-08-01 | TBA | N/A
11 | Nwadzekudzeku community hall | Vote to be Created | consultant | G/G/M/015/010/2021 | 1 | 1000000 | 1000000 |  | Competitve Bidding/PANEL | LGES | 2020-08-31 | 2020-09-18 | 2020-08-01 | TBA | N/A
12 | Blinkwater Upgrading of internal streets | Vote to be Created | consultant | G/G/M/015/011/2021 | 1 | 1000000 | 1000000 |  | Competitve Bidding/PANEL | LGES | 2020-08-31 | 2020-09-18 | 2020-08-01 | TBA | N/A
13 | Thomo Upgrading of internal streets | Vote to be Created | consultant | G/G/M/015/012/2021 | 1 | 1000000 | 1000000 |  | Competitve Bidding/PANEL | LGES | 2020-08-31 | 2020-09-18 | 2020-08-01 | TBA | N/A
14 | Nkuri Zamani Upgrading of internal streets | Vote to be Created | consultant | G/G/M/015/013/2021 | 1 | 1000000 | 1000000 |  | Competitve Bidding/PANEL | LGES | 2020-08-31 | 2020-09-18 | 2020-08-01 | TBA | N/A
15 | golf course development | C0316-1/IA01952/F0002/X006/R0230/001/6255 | consultant | G/G/M/015/013/2021 | 1 | 800000 | 800000 |  | competitevi bidding | LGES | 2020-08-31 | 2020-09-19 | 2020-08-02 | TBA | N/A
16 | servicing of 539 sites | Vote to be Created | consultant | G/G/M/015/013/2021 | 1 | 200000 | 200000 |  | competetive bidding | LGES | 2020-08-31 | 2020-09-18 | 2020-08-01 | TBA | N/A
17 | Shimange Upgrading from gravel to paving | Vote to be Created | consultant | G/G/M/015/014/2021 | 1 | 1000000 | 1000000 |  | Competitve Bidding/PANEL | LGES | 2020-08-31 | 2020-09-18 | 2020-08-01 | TBA | N/A
PMU sub-total | [5 empty] | 66100007 | 66100008 | 0 | [6 empty] | N/A
19 | GGM News letter | O1235-1/IE00755/F0041/X044/R0230/001/6057 | Consultant | G/G/M/015/016/2021 | 4 | 652000 |  | 652000 | Competitve Bidding | OWN | 2020-07-01 | 2020-02-26 | 2019-05-31 | 2022-04-30 | N/A
20 | Website redevelopment | Vote to be Created | Consultant | G/G/M/015/018/2021 | 1 | 150000 |  | 150000 | RFQ SITA | OWN | 2020-08-31 | 2020-09-30 | 2020-10-01 | 2021-06-30 | N/A
21 | Email Archiving | Vote to be Created | Consultant | G/G/M/015/019/2021 | 1 | 500000 |  | 500000 | Competitve Bidding | OWN | 2020-08-31 | 2020-09-30 | 2020-10-01 | 2021-06-30 | N/A
22 | Business Continuity Plan | Vote to be Created | Consultant | G/G/M/015/020/2021 | 1 | 200000 |  | 200000 | Competitve Bidding | OWN | 2020-08-31 | 2020-09-30 | 2020-10-01 | 2021-06-30 | N/A
23 | Disaster Recovery Plan | Vote to be Created | Consultant | G/G/M/015/020/2021 | 1 | 300000 |  | 300000 | Competitve Bidding | OWN | 2020-09-01 | 2020-10-01 | 2020-10-02 | 2021-07-01 | N/A
24 | GIS Upgrade | O0025-8/IE00853/F0041/X101/R0230/001/6155 | Consultant | G/G/M/015/021/2021 | 1 | 200000 |  | 200000 | Competitve Bidding | OWN | 2020-08-31 | 2020-09-30 | 2020-10-01 | 2021-06-30 | N/A
25 | Help desk sytem | C0086-1/IA04957/F0002/X052/R0230/001/6105 | Consultant | G/G/M/015/022/2021 | 1 | 300000 |  | 300000 | competitive bidding | OWN | 2020-08-31 | 2020-09-30 | 2020-10-01 | 2021-06-30 | N/A
26 | Street naming Giyani section A and F | Vote to be Created | Consultant | G/G/M/015/023/2021 | 1 | 800000 |  | 500000 | Competitve Bidding | OWN | 2020-08-31 | 2020-09-30 | 2020-10-01 | 2021-06-30 | N/A
27 | Street naming Giyani BA & Giyani C | Vote to be Created | Consultant | G/G/M/015/024/2021 | 1 | 500000 |  | 500000 | Competitve Bidding | OWN | 2020-08-31 | 2020-09-30 | 2020-10-01 | 2021-06-30 | N/A
28 | Subdivision, Rezoning & Registration of Municipal Properties in Villages and town | O0025-12/IE00001/F0041/X101/R0230/001/6155 | Consultant | G/G/M/015/025/2021 | 1 | 800000 |  | 800000 | Competitve Bidding | OWN | 2020-08-31 | 2020-09-30 | 2020-10-01 | 2021-06-30 | N/A
29 | Subdivision & Rezoning of remainder 1946 Giyani F | O0025-12/IE00001/F0041/X101/R0230/001/6155 | Consultant | G/G/M/015/025/2021 | 1 | 200000 |  | 200000 | Competitve Bidding |  | 2020-08-31 | 2020-09-30 | 2020-10-01 | 2021-06-30 | N/A
30 | Township Establishment Nsavulani village | Vote to be Created | Consultant | G/G/M/015/026/2021 | 1 | 500000 |  | 500000 | Panel of Suppliers | OWN | 2020-08-31 | 2020-09-30 | 2020-10-01 | 2021-06-30 | N/A
31 | formalisation of church view | Vote to be Created | Consultant | G/G/M/015/027/2021 | 1 | 300000 |  | 300000 | Panel of Suppliers | OWN | 2020-08-31 | 2020-09-30 | 2020-10-01 | 2021-06-30 | N/A
32 | Formalisation of Makosha Risinga Externsion | O1302-2/IE00855/F0041/X101/R0023/001/6155 | Consultant | G/G/M/015/027/2021 | 1 | 200000 |  | 200000 | competitevi bidding | OWN | 2020-08-31 | 2020-09-30 | 2020-10-01 | 2021-06-30 | N/A
33 | Review of LED Strategy | Vote to be Created | Consultant | G/G/M/015/028/2021 | 1 | 800000 |  | 800000 | Competitve Bidding | OWN | 2020-08-31 | 2020-09-30 | 2020-10-01 | 2021-06-30 | N/A
34 | Proclamation Programme | O0025-6/IE00001/F0041/X101/R0230/001/6155 | Consultant | G/G/M/015/028/2021 | 1 | 400000 |  | 400000 | Competitve Bidding | OWN | 2020-08-31 | 2020-09-30 | 2020-10-01 | 2021-06-30 | N/A
35 | Deeds Registration Of Sites | O0025-7/IE00001/F0041/X101/R0230/001/6155 | Consultant | G/G/M/015/028/2021 | 1 | 200000 |  | 200000 | Competitve Bidding | OWN | 2020-08-31 | 2020-09-30 | 2020-10-01 | 2021-06-30 | N/A
36 | Rezoning and Subdivision of Parks | O0025-9/IE00001/F0041/X101/R0416/001/6155 | Consultant | G/G/M/015/028/2021 | 1 | 500000 |  | 500000 | Competitve Bidding | OWN | 2020-08-31 | 2020-09-30 | 2020-10-01 | 2021-06-30 | N/A
37 | ICT Network Infrustructure | C0025-1/IA00052/F0002/X052/R0229/001/6105 | Consultant | G/G/M/015/029/2021 | 1 | 2500000 |  | 2500000 | Competitve Bidding | OWN | 2020-08-31 | 2020-09-30 | 2020-10-01 | 2021-06-30 | N/A
38 | panel of legal services | O0001/IE00008/F0041/X053/R0229/001/6108 | Consultant | G/G/M/015/030/2021 | 10 | 4000000 |  | 4000000 | Competitve Bidding | OWN | 2020-08-31 | 2020-09-30 | 2020-10-01 | 2021-06-30 | N/A
39 | pool of civils consultants | O0001/IE00008/F0041/X053/R0229/001/6108 | consultants | G/G/M/015/031/2021 | 10 | 4000000 |  | 4000000 | competitive bidding | OWN | 2020-08-31 | 2020-09-30 | 2020-10-01 | 2021-06-30 | N/A
40 | Automated audit System | Vote to be Created | Consultant | G/G/M/015/032/2021 | 1 | 200000 |  | 200000 | Competitve Bidding | OWN | 2020-08-31 | 2020-09-30 | 2020-10-01 | 2021-06-30 | N/A
41 | Alternative Road to Giyani from R81 | C0040-10/IA01952/F0002/X116/R0230/001/6601 | Consultant | G/G/M/015/033/2021 | 1 | 2000000 |  | 2000000 | Competitve Bidding | OWN | 2020-08-31 | 2020-09-30 | 2020-10-01 | 2021-06-30 | N/A
42 | Electrification of Nkuri Zamani village (200 units /stands) | Vote to be Created | contractor and consultant | Panel of Suppliers | 2 | 2250000 | 2250000 |  | Panel of Suppliers | ENEP | 01/07/2020 | N/A | 31/08/2020 | 31/08/2021 | N/A
43 | Electrification of Shimange village (100 units /stands) | Vote to be Created | contractor and consultant | Panel of Suppliers | 2 | 1800000 | 1800000 |  | Panel of Suppliers | ENEP | 01/07/2020 | N/A | 31/08/2020 | 31/08/2021 | N/A
44 | Electrification of Jim ngalalume village (200 units /stands) | Vote to be Created | contractor and consultant | Panel of Suppliers | 2 | 2250000 | 2250000 |  | Panel of Suppliers | ENEP | 01/07/2020 | N/A | 31/08/2020 | 31/08/2021 | N/A
45 | WiFi Access Points | Vote to be Created | contractor and consultant | competitive bidding | 1 |  |  |  | competitive bidding |  | 01/07/2020 | N/A | 31/08/2020 | 31/08/2021 | N/A
46 | Disaster Recovery Plan | Vote to be Created | contractor and consultant | competitive bidding | 1 |  |  |  | competitive bidding |  | 01/07/2020 | N/A | 31/08/2020 | 31/08/2021 | N/A
47 | Electrification of Mapuve village (200 units /stands) | Vote to be Created | contractor and consultant | Panel of Suppliers | 2 | 2250000 | 2250000 |  | Panel of Suppliers | ENEP | 01/07/2020 | N/A | 31/08/2020 | 31/08/2021 | N/A
48 | Electrification of Noblehook village (150 units /stands) | Vote to be Created | contractor and consultant | Panel of Suppliers | 2 | 1800000 | 1800000 |  | Panel of Suppliers | ENEP | 01/07/2020 | N/A | 31/08/2020 | 31/08/2021 | N/A
49 | Electrification of Mashavela village (150 units /stands) | Vote to be Created | contractor and consultant | Panel of Suppliers | 2 | 1374000 | 1374000 |  | Panel of Suppliers | ENEP | 01/07/2020 | N/A | 31/08/2020 | 31/08/2021 | N/A
50 | Electrification of Mashavela village (150 units /stands) | Vote to be Created | contractor and consultant | Panel of Suppliers | 2 | 426000 | 426000 |  | Panel of Suppliers | ENEP | 01/07/2020 | N/A | 31/08/2020 | 31/08/2021 | N/A
Consultant Sub-Total | [5 empty] | 19550000 | 0 | 19250000 | [6 empty] | N/A
51 | Asset register 2020/2021 | O0001/IE00830/F0930/X047/R0229/001/6114 | consultant | Panel of Suppliers | 1 | 4300000 |  | 4300000 | Panel of Suppliers | OWN | 2020-07-07 | N/A | 2021-01-31 | 2021-06-30 | N/A
52 | Automated Audit System | Vote to be Created | consultant | competitevi bidding | 1 | 200000 |  | 200000 | competetive bidding | OWN | 2020-08-31 | N/A | 2020-12-30 | 2024-01-01
53 | Automated PMS System | C0086-3/IA04957/F0041/X096/R0229/001/6151 | consultant | competitive bidding | 1 | 1170000 |  | 1177000 | competetive bidding | OWN | N/A | N/A |  | 2023-08-30 | N/A
54 | AFS preparation 2020/2021 | O0001/IE00830/F0930/X047/R0229/001/6114 | consultant | Panel of Suppliers | 1 | 3000000 |  | 3000000 | Panel of Suppliers | OWN | 2020-07-07 | N/A | 2021-01-31 | 2021-06-30 | N/A
55 | Calculation of PEMA & LSA Provisions | O0001/IE00830/F0933/X049/R0229/001/6117 | consultant | competitive bidding | 1 | 35000 |  | 35000 | Quotation Based | OWN | 2020-07-13 | 2020-07-22 | 2020-07-31 | 2020-08-13 | N/A
consultant Sub-Total | [5 empty] | 59955000 | 12150000 | 47177000
PPE Sub-Total | [5 empty] | 118760000 | 24300000 | 93239000
56 | Road Maintenance Material and Tools | O2392-1/IE00534/F0933/X116/R0230/001/6601 | Goods & Services | OPERATIONAL | As and When Required | 2500000 |  | 2500000 | Panel of Suppliers | Equitable Share | On-going | On-going | On-going | On-going | N/A
57 | Road and stormwater Maintenance (civils) | O2392-1/IE00080/F0933/X116/R0230/001/6601 | Goods & Services | OPERATIONAL | As and When Required | 32000000 |  | 3200000 | Panel of Suppliers | Equitable Share | On-going | On-going | On-going | On-going | N/A
58 | Electrical Maintenance Materials and Tools | O2385-1/IE00534/F0930/X032/R0230/001/6707 | Goods & Services | OPERATIONAL | As and When Required | 1300000 |  | 1300000 | Panel of Suppliers | Equitable Share | On-going | On-going | On-going | On-going | N/A
59 | Electrical Maintenance civils | O2385-2/IE00634/F0041/X032/R0229/001/6707 | Goods & Services | OPERATIONAL | As and When Required | 1500000 |  | 1500000 | Panel of Suppliers | Equitable Share | On-going | On-going | On-going | On-going | N/A
60 | Electrical air conditioners | C0004-3/IA06233/F0002/X032/R0229/001/6707 | Goods & Services | OPERATIONAL | As and When Required | 500000 |  | 500000 | Panel of Suppliers | Equitable Share | On-going | On-going | On-going | On-going | N/A
61 | Water and Sanitation Maintenance Materials and Tools | O2774-1/IE00534/F0041/X055/R0229/001/6107 | Goods & Services | OPERATIONAL | As and When Required | 2500000 |  | 2500000 | Panel of Suppliers | Equitable Share | On-going | On-going | On-going | On-going | N/A
62 | PMU Stationery | O0001/IE00534/F1182/X099/R0229/001/6055 | Goods & Services | OPERATIONAL | As and When Required | 40000 |  | 400000 | Competitve Bidding | MIG | 2020-08-31 | 2020-09-18 | 2020-09-30 | TBA | N/A
63 | Printers | Vote to be Created | Goods & Services | competitive bidding | 1 | 100000 |  | 100000 | competitive bidding |  | 01/07/2020 | N/A | 31/08/2020 | 31/08/2021 | N/A
64 | Projectors | Vote to be Created | Goods & Services | competitive bidding | 1 | 100000 |  | 100000 | competitive bidding |  | 01/07/2020 | N/A | 31/08/2020 | 31/08/2021 | N/A
65 | Property Maintenance Materials and Tools | O2774-1/IE00534/F0041/X055/R0229/001/6107 | Goods & Services | OPERATIONAL | As and When Required | 1000000 |  | 1000000 | Panel of Suppliers | Equitable Share | On-going | On-going | On-going | On-going | N/A
66 | purchase of tablets, printers and computer equipment | C0003-1/IA06173/F0002/X052/R0229/001/6105 | Goods & Services | OPERATIONAL | As and When Required | 28500000 |  | 2850000 | tranversal contract | Equitable Share | On-going | On-going | On-going | On-going | N/A
67 | Machine and equipment acquisition | C0006-1/IA06282/F0002/X050/R0229/001/6111 | Goods & Services | G/G/M/6111/034/2021 | transversal contract | 5000000 |  | 5000000 | tranversal contract | Equitable Share | 2020-07-01 | N/A | N/A | 2021-06-30 | N/A
68 | Purchase of vehicle | C0007-1/IA01327/F0002/X050/R0229/001/6111 | Goods & Services | G/G/M/6111/035/2021 | transversal contract | 3000000 |  | 3000000 | tranversal contract | Equitable Share | 2020-07-01 | N/A | N/A | 2021-06-30 | N/A
69 | Informantion Technology Maintenance Materials and Tools | C0003-5/IA06553/F0002/X052/R0230/001/6105 | Goods & Services | OPERATIONAL | As and When Required | 300000 |  | 300000 | Panel of Suppliers | Equitable Share | On-going | On-going | On-going | On-going | N/A
70 | Solid Waste Material and Toos | O0425-1/IE00651/F2496/X132/R0230/001/6501 | Goods & Services | OPERATIONAL | As and When Required | 250000 |  | 250000 | Panel of Suppliers | Equitable Share | On-going | On-going | On-going | On-going | N/A
71 | Community Services: Environmental Maintenance Material and Toos | C0006-3/IA06282/F0041/X132/R0230/001/6501 | Goods & Services | OPERATIONAL | As and When Required | 100000 |  | 100000 | Panel of Suppliers | Equitable Share | On-going | On-going | On-going | On-going | N/A
72 | walk through metal detector & exray machine | C0006-7/IA06282/F0002/X057/R0229/001/6351 | Goods & Services | OPERATIONAL | As and When Required | 200000 |  | 200000 | Competitve Bidding | Equitable Share | On-going | On-going | On-going | On-going | N/A
73 | Installation of cameras & monitor | C0006-4/IA06282/F0002/X057/R0229/001/6351 | Goods & Services | OPERATIONAL | As and When Required | 500000 |  | 500000 | Competitve Bidding | Equitable Share | On-going | On-going | On-going | On-going | N/A
74 | furniture and fittings | C0004-1/IA06233/F0002/X046/R0229/001/6109 | Goods & Services | OPERATIONAL | As and When Required | 1300000 |  | 1300000 | Panel of Suppliers | Equitable Share | On-going | On-going | On-going | On-going | N/A
75 | Mayors Cup | O1335-1/IE00571/F0041/X044/R0230/001/6057 | Goods & Services | OPERATIONAL | As and When Required | 500000 |  | 500000 | Panel of Suppliers | Equitable Share | On-going | On-going | On-going | On-going | N/A
76 | Diaster recovory plan | O1265-3/IE00571/F15762/X006/R0230/001/6353 | Goods & Services | OPERATIONAL | As and When Required | 5900000 |  | 5900000 | competetive bidding | Equitable Share | On-going | On-going | On-going | On-going | N/A
77 | HIV/Candle Lighting | Vote to be Created | Goods & Services | OPERATIONAL | As and When Required | 200000 |  | 200000 | quotation basis | Equitable Share | On-going | On-going | On-going | On-going | N/A
78 | Youth Support | Vote to be Created | Goods & Services | OPERATIONAL | As and When Required | 200000 |  | 200000 | quotation basis | Equitable Share | On-going | On-going | On-going | On-going | N/A
79 | Gender Support | Vote to be Created | Goods & Services | OPERATIONAL | As and When Required | 180000 |  | 180000 | quotation basis | Equitable Share | On-going | On-going | On-going | On-going | N/A
80 | Human Resources (Job evaluations) | O0001/IE00840/F0041/X051/R0229/001/6103 | Goods & Services | OPERATIONAL | As and When Required | 100000 |  | 100000 | quotation basis | Equitable Share | On-going | On-going | On-going | On-going | N/A
81 | Qualification Verification | O0001/IE00845/F0041/X051/R0229/001/6103 | Goods & Services | OPERATIONAL | As and When Required | 120000 |  | 120000 | quotation basis | Equitable Share | On-going | On-going | On-going | On-going | N/A
82 | Child & Oldage Support | Vote to be Created | Goods & Services | OPERATIONAL | As and When Required | 60000 |  | 60000 | quotation basis | Equitable Share | On-going | On-going | On-going | On-going | N/A
83 | Disability Support | Vote to be Created | Goods & Services | OPERATIONAL | As and When Required | 180000 |  | 180000 | quotation basis | Equitable Share | On-going | On-going | On-going | On-going | N/A
84 | Traditional Authority Support | Vote to be Created | Goods & Services | OPERATIONAL | As and When Required | 150000 |  | 150000 | quotation basis | Equitable Share | On-going | On-going | On-going | On-going | N/A
85 | Accomodation and meal for all depaerment | O0001/IE00060/F0041/X051/R0229/001/6103 | Goods & Services | OPERATIONAL | As and When Required | 0 |  | 0 | quotation basis | Equitable Share | On-going | On-going | On-going | On-going | N/A
86 | Event Management | Vote to be Created | Goods & Services | OPERATIONAL | As and When Required | 450000 |  | 450000 | quotation basis | Equitable Share | On-going | On-going | On-going | On-going | N/A
87 | Office Cleaning Materials and Tools | Vote to be Created | Goods & Services | OPERATIONAL | As and When Required | 700000 |  | 700000 | Panel of Suppliers | Equitable Share | On-going | On-going | On-going | On-going | N/A
88 | Intergrated Development Plan | O1336-1/IE00060/F0041/X096/R0229/001/6151 | Goods & Services | OPERATIONAL | As and When Required | 600000 |  | 600000 | Panel of Suppliers | Equitable Share | On-going | On-going | On-going | On-going | N/A
89 | Maintenance of Parks / Land Scape | O0017-1/IE00575/F0041/X006/R0230/001/6255 | Goods & Services | OPERATIONAL | As and When Required | 80000 |  | 80000 | Competitve Bidding | Equitable Share | On-going | On-going | On-going | On-going | N/A
90 | Standard Rated (Consumables) | 001/IE00738/F0041/X047/R0229/001/6113 | Goods & Services | OPERATIONAL | As and When Required | 500000 |  | 500000 | Panel of Suppliers | Equitable Share | On-going | On-going | On-going | On-going | N/A
91 | Office Printing and Stationery | O0001/IE00534/F0041/X047/R0229/001/6113 | Goods & Services | OPERATIONAL | As and When Required | 900000 |  | 900000 | Competitve Bidding | Equitable Share | On-going | On-going | On-going | On-going | N/A
Goods and Service Sub-Total and PPE sub-total | [5 empty] | 298480000 | 36450000 | 205798000
TOTAL | [5 empty] | 85650007 | 66100008 | 19250000
Legends:
I(I&S) | Infrastructure (Instalation and Supply)
G | Goods
S | Services
Q | Quotation
OT | Open Tender
CT | Closed Tender
BD/RPF | Bid documents/ Request for proposal
GGM | Greater Giyani Municipality
Note on B93: Khoza, J Purchase of Bins
Note on B97: Khoza, J (GGM): Sport Developmenet and Mayors Cup

## Sheet1
Email Archiving
IT Business Continuity Plan
Printers
WiFi Access Points
Disaster Recovery Plan
Projectors