## Sheet1
| FINANCIAL YEAR |  |  | 2018/19
| Municipality Name |  |  | Greater Giyani Municipality
| Audit Opinion |  |  | Qualified
Reporting Period
Finding No. | Audit Findings | Category of Finding | Commaf number | Description of Finding | Finding is new or recurring | Root Cause | Action Plan Description | Start Date | Completion Date | Person Responsible | Position | Progress | Narrative to Progress | Internal Audit Comments
1 | Employee Cost - Accuracy of Overtime | Employee costs | COMAF 60 | During the audit, it was discovered that the municipality had not paid the overtime that was worked in previous financial period but only settled those overtime in the 2018/2019 financial year. Upon inspection of the sample of the claims paid and the financial statement it was discovered the municipality did not raise a payable towards the employees that worked the overtime and not paid in prior financial periods. | New | Lack of proper review by Chief financial officer of the work done on HR which is recorded on the financial statement. | All overtime due at year end must be quantified and provided for as payables at 30 June every year for annual financial statement purposes. | 17/01/2020 | 30/04/2020 | Shiviti MT | Director Corporate Services
2 | Performance targets are not measurable | Predetermined objectives | Comaf 24 | Contrary to the stipulations, we noted that targets for the indicators listed hereunder are not measurable. during the audit of performance information, the annual performance report submitted for audit was noted to be inconsistent with the revised SDBIP | Recurring | Lack of review of documents to ensure that indicators and targets are developed as per the Framework for Managing Programme Performance Information (FMPPI) | Development of SDBIP process plan Issue SDBIP template to all Directors Conduct a session per Directorate for SDBIP development Directors should declare/sign off the information provided in the SDBIP Consolidate information received into a draft SDBIP | 17/01/2020 | 30/04/2020 | Rikhotso MJ | Manager PMS
3 | Performance indicator in the APR not consistent with the performance target | Predetermined objectives | Comaf 24 | Contrary to the stipulation, we noted that the information as contained in the annual performance report submitted for audit relating to the performance indicators and targets listed hereunder are not consistent. | Recurring | Prepare regular, accurate and complete financial and performance reports that are supported and evidenced by reliable information. | Development of SDBIP process plan Issue SDBIP template to all Directors Conduct a session per Directorate for SDBIP development Directors should declare/sign off the information provided in the SDBIP Consolidate information received into a draft SDBIP | 17/01/2020 | 30/04/2020 | Rikhotso MJ | Manager PMS
4 | Annual Performance Report (APR) inconsistent with the Service Delivery and Budget Implementation Plan (SDBIP) | Predetermined objectives | Comaf 24 | During the audit of performance information, we noted that the annual performance report submitted for audit was not consistent with the revised SDBIP with regards to the indicators listed hereunder, i.e. the indicators as on the revised SDBIP were not reported in the APR. The inconsistencies are as a result of planning documents not being reviewed regularly and compared to the reporting documents prior to submission for audit | Recurring | Prepare regular, accurate and complete financial and performance reports that are supported and evidenced by reliable information. | Collating of Annual Perfomance Report information by Perfomance Management System (PMS) Internal Audit division to conduct a review/audit of the Annual perfomance report Implementation of audit recommendations by PMS | 17/01/2020 | 30/04/2020 | Rikhotso MJ | Manager PMS
5 | Reported achievement differs with supporting information | Predetermined objectives | COMAF 61 | Contrary to the above requirement, during the audit of performance information, it was noted that the following performance indicator's reported achievements did not agree with achievement as per supporting documentation. | Recurring | Prepare regular, accurate and complete financial and performance reports that are supported and evidenced by reliable information. | Development and circulation of time schedule for submission of relevant POE's. Request Information Technology unit to insert auto reminder 3days prior the submission of perfomance report and POE's Development of a checklist by each department on submission of POE's,that will ensure alignment of each programme on the SDBIP with the actual POE's Internal Audit to review perfomamnce management reports | 17/01/2020 | 30/04/2020 | Rikhotso MJ | Manager PMS
6 | Procurement and Contract Management | Expenditure - The municipality traded with suppliers that were non-tax compliant at the time of the award | Comaf 29 | We noted that the municipality traded with suppliers that are non-tax compliant. | New | Management did not confirm the tax status of the suppliers prior trading with the suppliers. | 1. Quotation Central Supplier Database (CSD) status for the lowest bidder should be confirmed before the purchase order is issued and when payment is effected. 2. Pool of contractors CSD status should be confirmed: - Prior allocation of work - When payment is made 3. Section 32 / transversal contracts Confirmation of the contracts status. Ensure that the contract its aligned to the original contract of the originator. Confirmation of the CSD status of the contractor. | 17/01/2020 | 30/04/2020 | Maluleke GP | Manager SCM
7 | The final decision on which quotation to accept was made by an official with an interest in the supplier | Procurement and Contract Management | COMAF 34 | Contrary to the stipulated requirement, we have noted that a supplier who is a business associate of the official of the municipality in another company did not declare his/her interest when quoting for a bid as required on the SBD form. We further noted that the official who is the end user and Director of the department of specific service which was procured, was involve in the procurement process and did not declare his/her interest and therefore recuse him/herself from the process. The award was won by that specific related party. | New | Failure to comply with the municipal supply chain management regulations as a result of inappropriate oversight over controls and compliance monitoring to supply chain management prescripts. | Include the transaction in the irregular expenditure register and be referred to MPAC for investigation and recommendation. Declaration of interest should be signed by all Supply Chain Practitioners and all Bid Committee Members. Notify National Treasury to add defaulted suppliers on the database of restricted suppliers for wrongful declaration of MBD 4 form. Supply Chain Practitioners and all Bid Committee Members need to be trained on the roles and responsibilities. | 17/01/2020 | 30/04/2020 | Maluleke GP | Manager SCM
8 | The winning provider's tax matters has not been declared by SARS to be in order. | Procurement and Contract Management | COMAF 34 | Contrary to the above requirements, the CSD report for the supplier "Anric Enterprise" and noted that overall tax status of Anric Enterprise could not be determined at the time of the award. The expenditure incurred will result in irregular expenditure amounting to R 31 476,06 | New | The accounting officer did not ensure that adequate review and monitoring of compliance with applicable laws and regulations. | 1. Quotation Central Supplier Database (CSD) status for the lowest bidder should be confirmed before the purchase order is issued and when payment is effected. 2. Pool of contractors CSD status should be confirmed: - Prior allocation of work - When payment is made 3. Section 32 / transversal contracts Confirmation of the contracts status. Ensure that the contract its aligned to the original contract of the originator. Confirmation of the CSD status of the contractor. | 17/01/2020 | 30/04/2020 | Maluleke GP | Manager SCM
9 | The reasons for deviation do not appears reasonable/ justified on the basis that it was impossible/ impractical to obtain 3 written quotations | Procurement and Contract Management | COMAF 34 | Contrary to the above requirements, a reasonability test for the procurement of a new franking machine from a sole supplier (Hassler Business System) does not appear reasonable as we noted that there is more than one supplier of the franking machine therefore it could have been possible to follow the SCM process of obtaining three quotations. The expenditure incurred will result in irregular expenditure being incurred amounting to R 145 346, 20. | New | The accounting officer did not ensure that adequate review and monitoring of compliance with applicable laws and regulations. | All sole service providers should be confirmed in writing by South African Bureau Standards (SABS) All deviations should be approved by the Accounting Officer. Submission of deviation register to Internal Audit unit for review on a monthly basis. The deviation register should be accompanied by the POE | 17/01/2020 | 30/04/2020 | Maluleke GP | Manager SCM
10 | Regulation 32 contract was entered into beyond the scope of the original contract | Procurement and Contract Management | Comaf 40 | Contrary to the above stipulations, the Greater Giyani Municipality entered into a contract with a supplier beyond the term of the original contract as the contract with the other organ of state was under an extension contract. During the time when the contract was entered into with Mavambo ITS (Pty) Ltd, the original contract had already lapsed. The table below has details: | New | Failure to comply with the municipal supply chain management regulations as a result of inappropriate oversight over controls and compliance monitoring to supply chain management prescripts. | All payments made should be included in the irregular expenditure register and be referred to MPAC for investigation and recommendation. The following steps should be undertaken before section 32 appointment is made: -The municipality must confirm the duration of the contract between the service provider/s and the other organ of state and determine the remaining term of the contract. -The municipality will only be permitted to utilise the contract of the other organ of state for the balance of the remaining period of the contract. -The contract cannot be extended or varied, It can only be extended by the original contracting parties in line with the contractual terms agreed to in the original contract. -Should the contract between the original contracting parties be terminated for any reason before the contract end date, then that termination applies to the municipality contract as well. | 17/01/2020 | 30/04/2020 | Maluleke GP | Manager SCM
11 | The winning contractor's grading is not suitable for the value of contract | Procurement and Contract Management | COMAF 54 | Issue 1: The winning contractor (Titanic business enterprise) grading was not suitable for the value of the contract. Refer to the table below for details. Issue 2: The winning contractors (Titanic business enterprise) was awarded the contract though they were registered at a grade lower than the required grade. The margin with which the tenderer exceeded his/her tender value range is considered reasonable at no more than 15%. Issue 3: Section 62 (1) (c) of the MFMA states that “The accounting officer of a municipality is responsible for managing the financial administration of the municipality, and must for this purpose take reasonable steps to ensure that the municipality has and maintain, effective, efficient and transparent systems of financial and management and internal control”, Issue 4: The tender requirements for above mentioned tender did not include a condition for mandatory subcontracting to advance designated groups as required by PPR even though the amount was above R30 million. The expenditure incurred for the contract will result in irregular expenditure amounting to R6 679 087.53. | New | Failure to comply with the municipal supply chain management regulations as a result of inappropriate oversight over controls and compliance monitoring to supply chain management prescripts. | All payments made should be included in the irregular expenditure register and be referred to MPAC for investigation and recommendation. All tender document with an estimate above R30 Million should include the tender requirements for mandatory subcontracting to advance designated groups as required by PPPFA Review of all tender documents prior the advertisement by the CFO and the end-user department. | 17/01/2020 | 30/04/2020 | Maluleke GP | Manager SCM
12 | Inter Municipal Account: Amount disclosed in the AFS differs from the amount confirmed by Mopani District Municipality | Receivables | Comaf 38 | During the audit of receivable (from exchange transactions), we noted that the inter municipal account in the financial statements of both Mopani District Municipality (MDM) and Greater Giyani Municipality (GGM) do not agree. The differences are as follows: | Recurring | Lack of proper coordination between Greater Giyani Municipality and Mopani District Council that led to unresolved differences. Coordination between the district and the local municipalities is lacking. | The CFO should obtain/send confirmations of amounts from the district municipality on the 28 August 2020 to ensure that the inter-municipal transactions are accurately presented in both the Annual Financial Statements. | 17/01/2020 | 30/04/2020 | Mhangwana D | CFO
13 | Cash flow misstatement | Cash flow statements | Comaf 11 | The following audit differences were noted on the cash flow statement for the year ended 30 June 2019, this was due to the fact that management overstated cash receipt from customers and cash paid to suppliers and employees with a non cash Debt impairment. This does not result in overall net difference in the cash flow from operations. We further noted that management did not remove a non cash “interest on overdue account write-off ‘’ when calculating cash paid from suppliers which r=[esulted in 107525 misstatements. | New | Lack of proper review of the annual financial statements by the Chief Financial Officer prior to submission for audit purposes to ensure cash flow is prepared in terms of the applicable GRAP standards. | Review of AFS by Audit committee and independent reviewer with the following schedules (i) Asset register (ii)Payable age analysis (iii)Commitment register (iv)Receivable age analysis (v)Retention register (vi)Accrual listing (vii)Investment register (viii)Grant register (ix)Schedules of provisions (x)Accounting policies | 17/01/2020 | 30/06/2020 | Mhangwana D | CFO
14 | Prior year cash flow not properly corrected for misstatements | Cash flow statements | COMAF 11 | The following misstatements were noted on the prior year Cash Flow Statement, as a result of management overstating cash receipt from customers and cash paid to suppliers and employees with a non-cash debt impairment item. | New | Lack of proper review of the annual financial statements by the Chief Financial Officer prior to submission for audit purposes to ensure cash flow is prepared in terms of the applicable GRAP standards. | Development of schedule for all prior year adjustment which will show the impact which each adjustment have on the different components of the AFS (Statement of Fincial performance and other comprehensive income, statement of financial position, statement of cash flow, statement of net changes in equity and accompanying notes) | 17/01/2020 | 30/04/2020 | Mhangwana D | CFO
15 | Comparative amounts in the note misstated by R29 245.00 | Commitments | Comaf 8 | We noted during the audit that the amount of commitments as disclosed in note 40 to the financial statements has been misstated as a result of comparative amount relating to capital expenditure being inaccurately disclosed. Although the financial statements were reviewed on different levels including the consultants who are being paid the municipality, it is not clear as to how the misstatement could not have been identified/detected prior to submission of the financial statements for audit purposes | New | Lack of proper review of the annual financial statements by the Chief Financial Officer prior to submission for audit purposes. | Review of AFS by Audit committee and independent reviewer with the following schedules (i) Asset register (ii)Payable age analysis (iii)Commitment register (iv)Receivable age analysis (v)Retention register (vi)Accrual listing (vii)Investment register (viii)Grant register (ix)Schedules of provisions (x)Accounting policies | 17/01/2020 | 30/06/2020 | Mashau N | Manager Budget & Reporting
16 | Commitments: Recalculated commitments do not agree to the commitment schedule resulting in misstatements - R7 780 224.61 | Commitments | Comaf 19 | During the audit of commitments, we noted that the information relating to the projects listed hereunder as recorded in the Work-in Progress register (WIP) does not agree to the information as in the contract register and commitment schedule resulting in commitments being misstated. In some instances, these projects are been indicated either as work-in progress or completed but are being included as commitments at year end. From the misstatements identified, it is evident that registers are only updated just before year end and monthly reconciliations are not performed. The table below has details: | New | Prepare regular, accurate and complete financial and performance reports that are supported and evidenced by reliable information. | 1. Commitment register should be redesigned and include at least but not limited to the following: • Contract date signed, project commencement date, total contract value, total approved variation orders, prior expenditure, Net balance (contract value + variation orders - prior expenditure) • Total commitment current year (Total commitments current year, commitments settled, commitments remaining for current year) • Commitment balance (net balance – commitment paid for the current year) 2. Only active contracts should be reflected in the Contract Register supported by the signed contracts including approved variation orders. 3. The Commitment Register should be aligned to the Contract Register | 17/01/2020 | 30/04/2020 | Mashau N. Maluleke GP and Nkuna F | Manager Budget, Manager SCM and Manager Asset
17 | Incorrect calculation used for car allowance resulting in misstatements: R5 913 399.21 | Employee costs | Comaf 26 | Contrary to the stipulations, we noted that the amounts for car allowance as disclosed in note 29 to the financial statements has been misstated as a result of incorrect calculation used. The AA rate was not applied in this case and the increase on the car allowance was based on the annual salary increase of 7%. In terms of the AA calculator the cost price Incl VAT is used to determine the km rate per car and the municipality used the annual salary of the employees. Due to limited information in the personal files regarding the details of the employees’ vehicles, we used one of the municipality’s employee’s vehicle information to calculate the car allowance to confirm the accuracy of the allowance. Refer to tables below for the calculations: | New | Incorrect application of the AA rates calculation due to lack of proper review of the calculation of the car allowance based on the approved policy. | An addendum to be made to rectify paragraph 8 &11 of the car allowance policy which deals with the basis for the payment for car allowances. Addendum will be submitted to council for noting All car allowance paid should be reffered to MPAC for investigation and recommendation. | 17/01/2020 | 30/04/2020 | M.T. Shiviti | Director Corporate Services
18 | Employee Cost: Long service incorrectly classified | Employee costs | COMAF 60 | During the audit of employee benefit obligation, it was discovered that the information given to the actuaries is not complete as details of employees listed hereunder were either incomplete or not included in the data provided to the actuaries. | New | Inadequate review of information by the Chief Financial Officer prior to submission to the actuaries. | Review of all details of employee by Expenditure Management unit before submission to actuaries | 17/01/2020 | 30/04/2020 | Mr J. Shivambu | Manager Expenditure
19 | Employee related costs: Employee benefit obligation expenses understated | Employee costs | COMAF 60 | During the audit it was discovered that the expense for employee benefit obligation was calculated as the difference between closing balance of current year and prior year. In terms of GRAP 25 long service should not be disclosed in the employee related costs, only the service costs and interest cost should be disclosed under employee related cost at R3517367 | New | Financial and performance management Lack of proper review of work before preparing financials. | Review of AFS by Audit committee and independent reviewer with the following schedules (i) Asset register (ii)Payable age analysis (iii)Commitment register (iv)Receivable age analysis (v)Retention register (vi)Accrual listing (vii)Investment register (viii)Grant register (ix)Schedules of provisions (x)Accounting policies | 17/01/2020 | 30/06/2020 | Mr J. Shivambu | Manager Expenditure
20 | Employee cost: Incorrect classification of councilors remuneration to employee related costs | Employee costs | COMAF 53 | During the audit of employee cost we noted that the amount related to the back pay and skills development levy for councilors was incorrectly included in the employee related costs, below is a table that shows the difference: | New | Lack of proper review by Chief Financial Officer of the work done on HR which is recorded on the financial statement. | The annual financial statement should be reconciled against trial balance, general ledger and the following supporting schedules (i) Asset register (ii)Payable age analysis (iii)Commitmnet register (iv)Receivable age analysis (v)Retention register (vi)Acrual listing (vii)Investment register (viii)Grant register (ix)Schedules of provisions (Actuarial report, Leave bonus, landfill site, Impairment, Long service, cost employment benefit, Workmen’s compensation (ixx)Unauthorised ,irregular and fruitless and wastefull expenditure (Including MPAC recomendations) All reconciliations should be reviewed and signed off by the CFO | 17/01/2020 | 30/06/2020 | Mr J. Shivambu | Manager Expenditure
21 | Employee Cost: Rental agreement not of signed by MM and Employees are in areas with rentals | Employee costs | COMAF 60 | During the audit it was discovered that the municipality does not follow the terms stipulated in the contracts between employees and the municipality for the residential renting of municipal properties. Through inspection of the contract and the payroll report it was discovered that the employees do not pay as per agreement in the contract and are in areas of the rental amount as well as other municipal services. The following table shows the balances owed by the employees which is a breach of contract and no further steps taken by the municipality | New | Lack of proper internal control on rental of municipalities property | Development of Municipal Property Rental policy and a rental policy agreement | 17/01/2020 | 30/04/2020 | Bamuza A | Manager Town Planning
22 | Employee benefit obligation overstated | Employee costs | COMAF 60 | During the audit of employee benefit obligation, it was discovered that the information given to the actuaries is not complete as details of employees listed hereunder were either incomplete or not included in the data provided to the actuaries. | New | Inadequate review of information by the Chief Financial Officer prior to submission to the actuaries. | Review of all details of employee by Expenditure Management unit before submission to actuaries | 17/01/2020 | 30/04/2020 | Mr J. Shivambu | Manager Expenditure
23 | Internal Audit is not being reviewed externally | Other matter – Control deficiency | Comaf 3 | we noted that the internal audit unit of the municipality has not been reviewed externally for the past 5 years. The internal audit, in performing their internal audit work, may not follow the code of ethics and the standards set by the Institute of the Internal Auditors The internal audit, in performing their internal audit work, may not conform to the Code of Ethics and the standards set by the Institute of the Internal Auditors. | New | The internal audit unit, in performing their internal audit work, did not follow/obey the code of ethics and the standards set by the Institute of the Internal Auditors. | Request a panel of CAE's from Mopani District Municipalities to conduct state of readiness (periodic reiview) Set aside budget during 2020/21 financial year for the appointment of external assessor. | 17/01/2020 | 30/04/2020 | Khosa G | Internal Audit Manager
24 | Employees' performance was not regularly monitored and evaluated based on predetermined criteria in the 2018/19 financial year. | Other matter – Control deficiency | Comaf 10 | During the process of obtaining understanding of the internal controls of the municipality, we identified that the Performance Management Systems policy is currently not being implemented as management only monitors the performance of employees who are a section 54 (Municipal Manager) level and sections 56 (Director) level. We further noted that the quarterly performance assessments for section 54 and section 56/54A were not performed for the 2018/19 financial year | Recurring | Management failed to exercise oversight responsibility regarding financial and performance reporting and compliance as well as related internal controls. | 1. Issue out the assessment template to directors for scoring 2. Receive the scored template together with the POE’s from directors 3. Perform performance audit 4. Submit the assessment scorecards together with the POE’s to Internal Audit for auditing 5. Receive back the audited scorecards from internal audit 6. Send out invitation to the panel members and conduct mid-year performance assessments | 17/01/2020 | 1. 29/01/2019 2. 12/02/2020 3. 13/2/2020 4. 17/2/2020 5. 25/02/2020 6. 27&28/02/2019 | Rikhotso MJ | Manager PMS
25 | Irregular Expenditure: Incorrect condonement amount disclosed in the AFS resulting in mistatements: (-R1 548 678.00) | Other matter – Control deficiency | Comaf 20 | We noted that the amount as disclosed in note 49 to the financial statements relating to condonement of irregular expenditure differs with the amount written-off as per the investigation report by Municipal Public Accounts Committee (MPAC) submitted for audit dated 29 August 2019. We further noted that, the disclosure on note 49 & 47 refers to condonation of Irregular and fruitless and wasteful while it was a write off by council, this is contrary to the Treasury regulations and MFMA as write off and condonation are materially different. | Recurring | Lack of proper review of the annual financial statements by the Chief Financial Officer prior to submission for audit purposes. | The annual financial statement should be reconciled against trial balance, general ledger and the following supporting schedules (i) Asset register (ii)Payable age analysis (iii)Commitmnet register (iv)Receivable age analysis (v)Retention register (vi)Acrual listing (vii)Investment register (viii)Grant register (ix)Schedules of provisions (Actuarial report, Leave bonus, landfill site, Impairment, Long service, cost employment benefit, Workmen’s compensation (ixx)Unauthorised ,irregular and fruitless and wastefull expenditure (Including MPAC recomendations) All reconciliations should be reviewed and signed off by the CFO | 17/01/2020 | 30/06/2020 | Maluleke GP | Manager Supply Chain Management.
26 | Expenditure - List of households receiving free basic electricity is not valid. | Other matter – Control deficiency | Comaf 29 | The list of all households receiving free basic electricity has duplicates of the ID numbers, the customer names and addresses. Therefore, we could not confirm the validity of the expenses. Examples are as follows: There are more than 1000 people sharing one ID number There are different addresses belonging to the same individual There is one address belonging to more than 3 individuals | New | Management did not review the list of households receiving free basic electricity. | Free Basic Electricity (FBE) database verification should be conducted to resolve the following: > Duplicate ID Numbers > Duplicate Customer Names > Duplicate Addresses All FBE applications to be supported by certified ID, proof of income or affidavit. > Conduct a second review of all applications before recording into the FBE database | 17/01/2020 | 30/04/2020 | Baloyi E | Senior Technician Electricity
27 | UIF incurred but the MEC and the Auditor-General were not informed | Other matter – Control deficiency | Comaf 27 | Contrary to the stipulation, we noted that the municipality had incurred unauthorised and fruitless and wasteful expenditure for the year under review which management failed to inform the MEC of local government in the province as well as the Auditor-General. This has resulted in non-compliance. | New | The Accounting Officer did not comply with the applicable legislation. | A report on unauthorised, irregular or fruitless and wasteful expenditure together with the steps that have been taken to recover or rectify such expenditure; and to prevent a recurrence of such expenditure should be submitted to MEC for local government and Auditor General on a quarterly basis A file for Portfolio of evidence should be kept by the office of the CFO | 17/01/2020 | 30/04/2020 | N Mashau | Manager – Budget & Reporting
28 | Payables - Controls to clear the unspecified deposits account are inadequate. | Other matter – Control deficiency | Comaf 33 | During the audit of payables, we noted that the suspense account relating to unspecified deposits is not been cleared timeously which might lead to an overstatement of payables. The process to allocate unspecified deposits is not appropriately designed to prevent, detect and correct errors. There is a risk of: Processes and controls may not correct the misstatements in the current year. | New | Process to allocate the unspecified deposits is not appropriate. | Development and implementation the unallocated deposit policy for 2019/2020 | 17/01/2020 | 30/04/2020 | Muhlari N | Manager Revenue
29 | Use of consultants - No training and transfer of skills from consultants to employees | Other matter – Control deficiency | COMAF 62 | Contrary to the Municipal SCM guide, the municipality entered into contracts that included important components for training or transfer of knowledge and skills but the terms of reference did not outline an objective for transfer of skills. The contracts are as follows: • Cathu Consulting Inc. - AFS preparation and training of staff • Morar Incorporated - GRAP compliant register • MOD Hope Properties - Provision of general valuation and compilation of the valuation roll These are the things that were not outlined in the contracts: 1. The terms of reference did not outline an objective for transfer of skills, including the nature, scope and goals of the training programme. 2. The following details regarding transfer of skills were not included in the terms of reference: i) employees to be trained; ii) skills to be transferred; iii) Monitoring and evaluation arrangements 3. The consultants’ contracts do not include a clause for transfer of skills. 4. Measures to monitor the transfer of skills in the projects are not implemented 5. Employees to be trained have not been identified | Recurring | Management did not review the contracts to ensure that the terms of reference outlines an objective for transfer of skills. | Approval of the draft standard operating procedure manual on the use of consultants by the Accounting Officer All service level agreements should include a clause for skills transfer (skills transfer plan) Service provider performance assessment to be conducted on a quarterly basis Service provider should provide quarterly reports on skills transfer | 17/01/2020 | 30/04/2020 | Maluleke GP | Manager SCM
30 | Strategic planning and budgeting - Late submission of the adopted Integrated Development Plan (IDP) to the MEC of COGHSTA. | Other matter - Compliance | Comaf 6 | Contrary to the stipulation, we noted that the Municipality’s adopted IDP was not submitted to the MEC of local government within the stipulated period of time resulting in non-compliance with the act | Recurring | Lack of review and monitoring of compliance with applicable laws and regulations | Development of institutional compliance calendar Compliance calendar should be a standing item on monthly management meetings | 17/01/2020 | 30/04/2020 | Mabunda SL | IDP Manager
31 | Not all the requirement of MFMA additional disclosures are being disclosed in the AFS | Other matter - Compliance | Comaf 12 | Contrary to the stipulations, we noted that the municipality’s financial statement does not disclose all the required information as noted above. The following were omitted or not disclosed appropriately: 1. The municipality did not disclose taxes, duties, pension and medical aid contributions made during the year along with outstanding balance at year end. The municipality did not also disclose the contributions made to organized local government such as SALGA and other bodies. 2. The municipality disclosed all the required information for grant in terms of GRAP however the notes does not cover all the required information by section 123 of MFMA as it does not demonstrate from whom is the grant received from or if the grant were delayed or not spent in terms of the relevant DORA requirement. We further noted that the deviations for the year were disclosed, however we noted that what is being included in the register provided for audit purposes and the AFS do not reconcile. The table below has details: | New | Lack of review of the MFMA requirement by management to ensure compliance. | Alignment of Caseware prepared AFS to the National Treasury mSCOA AFS compliant template | 17/01/2020 | 30/06/2020 | Mhangwana D | CFO
32 | Expenditure: Payments were made after 30 days from receipt of invoice from suppliers. | Other matter - Compliance | Comaf 29 | During the testing of the expenditure it was noted that the following suppliers were not paid within 30 days from receipt of invoices | Recurring | Management didnot implement measures to ensure that paymentsto suppliers aremade within 30 days from date of receipt of invoice from suppliers. | Centralization of receipt of departmental invoices to the office of the Departmental Directors through Secretariat. Development of standardised suppliers invoice register Secretariat should record the invoice received on the suppliers invoice register All invoices should be stamped on the date of receipt All outgoing suppliers invoice should be signed for on collection | 17/01/2020 | 30/04/2020 | Mr J. Shivambu | Manager Expenditure
33 | Risk management disclosure not in line with GRAP104 | Other matter – Financial matter | Comaf 7 | During the audit of note 44 we noted that the municipality did not comply with the disclosure requirement of GRAP 104 as they did not disclosure the impact of Other financial assets-VBS investment on the entity for the credit exposure to the municipality along with the description thereof as required by GRAP 104:129. We further noted that impact of finance lease liability liquidity risk is also not disclosed as required by GRAP along with the required descriptions required by the standard. We furthermore identified that some of the description on credit risk maybe misleading as the municipality does not or did not only invest with major banks in both the comparative as the VBS investment is still part of their financial statement. Refer to the statement below: ‘Credit risk consists mainly of cash deposits, cash equivalents, derivative financial instruments and trade debtors. The municipality only deposits cash with major banks with high quality credit standing and limits exposure to any one counter-party.’ | Recurring | Lack of proper review of the annual financial statements by the Chief Financial Officer prior to submission to ensure that they are in compliance with GRAP. | Benchmarking with other municipalities that obtained clean audit to ensure compliance with the disclosure requirements of GRAP 104. Risk Management section should compile a quarterly financial risk exposure register. Quarterly financial risk exposure register should be utilised on the preparation of the quarterly financial statements. | 17/01/2020 | 30/04/2020 | Mhangwana D | CFO
34 | VAT: Opening balance as per AFS does not agree to opening balance as per GL: R33 693.46 | Value added tax | Comaf 13 | During the audit of VAT, it was noted that the opening balance as per the annual financial statements (AFS) does not agree to the opening balance in the general ledger (GL). | New | Lack of proper review of the annual financial statements by the Chief Financial Officer to ensure that accurate and complete financial reports are supported and evidenced by reliable information. | The annual financial statement should be reconciled against trial balance, general ledger and the following supporting schedules (i) Asset register,operating lease register and finance lease register (ii)Payable age analysis (iii)Commitmnet register (iv)Receivable age analysis (v)Retention register (vi)Acrual listing (vii)Investment register (viii)Grant register (ix)Schedules of provisions (Actuarial report, Leave bonus, landfill site, Impairment, Long service, cost employment benefit, Workmen’s compensation (iix)Unauthorised ,irregular and fruitless and wastefull expenditure (Including MPAC recomendations) (x) A reconciliation between the budget and trial balance All reconciliations should be reviewed and signed off by the CFO | 17/01/2020 | 30/06/2020 | Mhangwana D | CFO
35 | VAT amount as per the AFS does not agree to the amount as per the GL: R33 693.46 | Value added tax | COMAF 13 | During the audit of VAT, it was noted that the opening balance as per the annual financial statements (AFS) does not agree to the opening balance in the general ledger (GL). | New | Lack of proper review of the annual financial statements by the Chief Financial Officer to ensure that accurate and complete financial reports are supported and evidenced by reliable information. | The annual financial statement should be reconciled against trial balance, general ledger and the following supporting schedules (i) Asset register,operating lease register and finance lease register (ii)Payable age analysis (iii)Commitmnet register (iv)Receivable age analysis (v)Retention register (vi)Acrual listing (vii)Investment register (viii)Grant register (ix)Schedules of provisions (Actuarial report, Leave bonus, landfill site, Impairment, Long service, cost employment benefit, Workmen’s compensation (iix)Unauthorised ,irregular and fruitless and wastefull expenditure (Including MPAC recomendations) (x) A reconciliation between the budget and trial balance All reconciliations should be reviewed and signed off by the CFO | 17/01/2020 | 30/06/2020 | Mhangwana D | CFO
36 | Vat - Incomplete disclosure of VAT accounting policy | Value added tax | Comaf 16 | Contrary to the requirement, we noted that the accounting policy on VAT does not indicate the basis of measurement and the recognition of VAT in the financial statements. Incomplete disclosure of VAT accounting policy. | New | Prepare regular, accurate and complete financial and performance reports that are supported and evidenced by reliable information. | Deliverables in the SLA for independent reviewer should at least include but not limited to the following: 1. Alignment of Council approved policties against AFS policies and GRAP standards. 2. Ensure that all presentations and disclosures as requred by GRAP are adhered to 3. Submission of formal report upon conclusion of the review. | 17/01/2020 | 30/04/2020 | Shivambu J | Manager Expenditure
37 | Irregular expenditure: Amount written-off differs with the amount condoned resulting in misstatements: R1 548 678.88 | Irregular expenditure | Comaf 20 | Contrary to the stipulations, we noted that the amount as disclosed in note 49 to the financial statements relating to condonement of irregular expenditure differs with the amount written-off as per the investigation report by Municipal Public Accounts Committee (MPAC) submitted for audit dated 29 August 2019 | New | Lack of proper review of the annual financial statements by the Chief Financial Officer prior to submission for audit purposes. | The annual financial statement should be reconciled against trial balance, general ledger and the following supporting schedules (i) Asset register,operating lease register and finance lease register (ii)Payable age analysis (iii)Commitmnet register (iv)Receivable age analysis (v)Retention register (vi)Acrual listing (vii)Investment register (viii)Grant register (ix)Schedules of provisions (Actuarial report, Leave bonus, landfill site, Impairment, Long service, cost employment benefit, Workmen’s compensation (iix)Unauthorised ,irregular and fruitless and wastefull expenditure (Including MPAC recomendations) (x) A reconciliation between the budget and trial balance All reconciliations should be reviewed and signed off by the CFO | 17/01/2020 | 30/06/2020 | Mhangwana D | CFO
38 | Unauthorised expenditure: Amount as per schedule does not agree to the amount disclosed: R95 828 | Unauthorised expenditure | Comaf 21 | We noted during the audit that the amount of unauthorised expenditure as disclosed in note 48 to the financial statements does not agree to the schedule submitted for audit resulting in misstatements. Although the financial statements were reviewed on different levels including the consultants who are being paid by the municipality, it is not clear as to how the misstatement could not have been identified/detected prior to submission of the financial statements for audit purposes. | New | Lack of proper review of the annual financial statements by the Chief Financial Officer prior to submission for audit purposes. | The annual financial statement should be reconciled against trial balance, general ledger and the following supporting schedules (i) Asset register,operating lease register and finance lease register (ii)Payable age analysis (iii)Commitmnet register (iv)Receivable age analysis (v)Retention register (vi)Acrual listing (vii)Investment register (viii)Grant register (ix)Schedules of provisions (Actuarial report, Leave bonus, landfill site, Impairment, Long service, cost employment benefit, Workmen’s compensation (iix)Unauthorised ,irregular and fruitless and wastefull expenditure (Including MPAC recomendations) (x) A reconciliation between the budget and trial balance All reconciliations should be reviewed and signed off by the CFO | 17/01/2020 | 30/06/2020 | Mashau N | Manager Budget & Reporting
39 | Statement of comparison of Budget and Actual amounts: Misstatements | Statement of comparison of budget and actual amounts | COMAF 36 | We noted a difference in general expenses between the actual column of the Statement of comparison between budget and actual amounts and the amount as per the trial balance and the AFS. | New | There was a mapping error on general expenses on the Statement of Comparison of Budget | The annual financial statement should be reconciled against trial balance, general ledger and the following supporting schedules (i) Asset register,operating lease register and finance lease register (ii)Payable age analysis (iii)Commitmnet register (iv)Receivable age analysis (v)Retention register (vi)Acrual listing (vii)Investment register (viii)Grant register (ix)Schedules of provisions (Actuarial report, Leave bonus, landfill site, Impairment, Long service, cost employment benefit, Workmen’s compensation (iix)Unauthorised ,irregular and fruitless and wastefull expenditure (Including MPAC recomendations) (x) A reconciliation between the budget and trial balance All reconciliations should be reviewed and signed off by the CFO | 17/01/2020 | 30/06/2020 | Mashau N | Manager Budget & Reporting
40 | Statement of comparison: Budget was adjusted but no disclosure made as required by GRAP 24 explaining the adjustments made. | Statement of comparison of budget and actual amounts | Comaf 38 | Contrary to paragraph 27 of GRAP, the municipality did not disclose explanations of the changes between the approved budget and the final budget. | Recurring | Management did not disclose explanations of the changes between the approved budget and the final budget. | Prepare a disclosure note for budget related information in accordance with GRAP 24 Deliverables in the SLA for independent reviewer should at least include but not limited to the following: 1. Alignment of Council approved policties against AFS policies and GRAP standards. 2. Ensure that all presentations and disclosures as requred by GRAP are adhered to 3. Submission of formal report upon conclusion of the review. | 17/01/2020 | 30/04/2020 | Mashau N | Manager Budget & Reporting
41 | Statement of comparison: No explanations were disclosed for the material variances between the budget and the actual amounts | Statement of comparison of budget and actual amounts | Comaf 38 | Contrary to paragraph 12(C) of GRAP 24, the municipality did not provide explanations for the following material variances: | New | Management did not provide explanations for material variances. | Prepare a disclosure note for budget related information in accordance with GRAP 27 Deliverables in the SLA for independent reviewer should at least include but not limited to the following: 1. Alignment of Council approved policties against AFS policies and GRAP standards. 2. Ensure that all presentations and disclosures as requred by GRAP are adhered to 3. Submission of formal report upon conclusion of the review. | 17/01/2020 | 30/04/2020 | Mashau N | Manager Budget & Reporting
42 | Safeguarding of inventory | Inventory | COMAF 49 | During our surprise visits at the two storerooms belonging to the municipality where inventory is being held, we noted that inventories are not properly safeguarded based on the following: • On arrival the door to the storeroom was not locked • Access to the storeroom is not restricted to authorised personnel • There are no controls in place over the movement of cars coming in and going out of the premises as security personnel does not exercise its responsibilities by examining those cars on their way out. Controls of inventory safeguard not operating effectively to prevent or detect theft of municipality inventory. Inventory could be easily stolen and not be noticed by security guard due to control deficiency. This creates a risk of existence assertion of inventory. | New | The accounting officer of the municipality has not ensured proper safeguarding of inventory at all times to avoid loss or theft of municipality inventory. | Instalation of CCTV cameras. Installation of palisade fence in the inner perimeter of the store room. Instalation of Biometric system to record the movement of personnel in and out of the storeroom. Enhancement of security services at storerooms (e.g capacitating securities and / outsourcing) | 17/01/2020 | 30/04/2020 | Maluleke GP | Manager SCM
43 | Inventory accounting policy not complete | Inventory | COMAF 55 | Contrary to the stipulation, we noted that the accounting policy for inventory does not include a cost formula, i.e. first-in, first-out or weighted average cost formula. Incomplete disclosure of inventory policy might lead to incorrect valuing of inventory. | Recurring | Prepare regular, accurate and complete financial and performance reports that are supported and evidenced by reliable information. | Review of AFS by Audit committee and independent reviewer with the following schedules (i) Asset register (ii)Payable age analysis (iii)Commitment register (iv)Receivable age analysis (v)Retention register (vi)Accrual listing (vii)Investment register (viii)Grant register (ix)Schedules of provisions (x)Accounting policies | 17/01/2020 | 30/06/2020 | Maluleke GP | Manager SCM
44 | Investment Property not completely recorded in the FAR. | Investment property | COMAF 48 | During the audit of investment property, we identified two properties which were not recorded as assets of the municipality in the fixed assets register. | New | Lack of proper review of the fixed asset register by the Chief Financial Officer prior to submission for audit purposes. | To conduct deeds search to identify all the properties that belongs to the Municipality by 30 June 2020 Based on the results of the deeds search, a property physical verification to confirm existence should be perfomed | 17/01/2020 | 30/04/2020 | Nkuna F | Manager Assets
45 | Disclosure for Other financial assets not in line with paragraph 105 of GRAP 104 | Investments | Comaf 9 | During the audit of other financial assets as disclosed in note 7 to the financial statements, we noted that the municipality did not disclose information necessary to enable the users of the financial statements to evaluate the significance of the investment in VBS and the impairment thereof as required by paragraph 105 of the reporting framework. | New | Lack of proper review of the annual financial statements by the Chief Financial Officer prior to submission for audit to ensure that there are in compliance with GRAP. | Deliverables in the SLA for independent reviewer should at least include but not limited to the following: 1. Alignment of Council approved policties against AFS policies and GRAP standards. 2. Ensure that all presentations and disclosures as requred by GRAP are adhered to 3. Submission of formal report upon conclusion of the review. | 17/01/2020 | 30/04/2020 | Mashau N | Manager Budget and Reporting
46 | Expenditure: Lease rentals on operating leases have been overstated | Leases | Comaf 29 | During the reasonability of operating leases we noted that the figure in the AFS has been overstated by R 121 488.37 and the difference is due to a general expense account amounting that was misclassified to operating leases. | New | Management did not adequately review the AFS before submission to auditors. | The annual financial statement should be reconciled against trial balance, general ledger and the following supporting schedules (i) Asset register,operating lease register and finance lease register (ii)Payable age analysis (iii)Commitmnet register (iv)Receivable age analysis (v)Retention register (vi)Acrual listing (vii)Investment register (viii)Grant register (ix)Schedules of provisions (Actuarial report, Leave bonus, landfill site, Impairment, Long service, cost employment benefit, Workmen’s compensation (iix)Unauthorised ,irregular and fruitless and wastefull expenditure (Including MPAC recomendations) (x) A reconciliation between the budget and trial balance All reconciliations should be reviewed and signed off by the CFO | 17/01/2020 | 30/06/2020 | F Nkuna | Manager - Assets
47 | 47. ISS.76-COMAF 59 - PPE: Inappropriate description and Assets Derecognised not removed from FAR | Movable assets | COMAF 59 | During the audit of Property, Plant and Equipment we identified the following: 1. Assets which are written off in the prior years were not removed from the Fixed Assets Register. Refer to annexure A for a sample of the assets with unclear descriptions. 2. Assets do not have clear descriptions that make it easy and convenient to trace the asset. Refer to annexure B for a sample of the assets not removed from the FAR. | New | Lack of proper review of the fixed asset register by the Chief Financial Officer prior to submission for audit purposes. | Issue 1 All assets written off during the year should be kept on a separate register and supported by the council resolution. Issue 2 Review Fixed Assets Register to identify assets with no descriptions and update accordingly. | 17/01/2020 | 30/04/2020 | F Nkuna | Manager - Assets
48 | Assets - Incorrect calculation of depreciation | Movable assets | COMAF 46 | During the audit of Property Plant and Equipment, we identified that depreciation was incorrectly calculated. This result in overstatement of depreciation by R382, 392.31. Refer to the appendix B for the list of assets on which an error was identified. | New | Lack of proper review of the fixed asset register by the Chief Financial Officer prior to submission for audit purposes. | Alignment of deprecition rates between Fixed Asset register and Asset Management Policy Recalculate the entire depreciation charge on the Fixed Asset Register. Effect the necessary adjustments in terms of GRAP 3 | 17/01/2020 | 30/04/2020 | F Nkuna | Manager - Assets
49 | Reported achievements verified in the prior year (2017/18) but still appearing in the 2018/19 Service Delivery Budget and Implementation Plan (SDBIP) and Annual performance Report (APR) | Predetermined objectives | Comaf 25 | Contrary to the above requirement, during the audit of performance information, it was noted that the following performance indicator's reported achievements were attained in the prior year (2017/18), thus they are overstating the 2018/19 performance information. | New | Prepare regular, accurate and complete financial and performance reports that are supported and evidenced by reliable information. | Development of SDBIP process plan Issue SDBIP template to all Directors Conduct a session per Directorate for SDBIP development Directors should declare/sign off the information provided in the SDBIP Consolidate information received into a draft SDBIP | 17/01/2020 | 30/04/2020 | Manager: PMS | Rikhotso MJ
50 | Targets indicated as achieved in the APR but were actually not attained | Predetermined objectives | Comaf 25 | Contrary to the stipulations, the indicators listed hereunder as well as their related targets were actually not achieved for the year under review based on the portfolio of evidence provided by management resulting in the actual/reported achievement being misstated in the annual performance report. | New | Prepare regular, accurate and complete financial and performance reports that are supported and evidenced by reliable information. | PMS and Internal audit to Conduct physical verification against reported progress and portfolio of eveidence on the annual perfomance report | 17/01/2020 | 30/04/2020 | Manager: PMS | Rikhotso MJ
51 | Reported achievements verified in the prior year (2017/18) but still appearing in the 2018/19 Service Delivery Budget and Implementation Plan (SDBIP) and Annual performance Report (APR) | Predetermined objectives | Comaf 25 | Contrary to the stipulations, we noted the indicators listed hereunder as well as their related targets were planned for, achieved and reported in the prior year (2017/18) but still appearing in the current year SDBIP and APR thus overstating the reported achievement. | New | Lack of proper review of the annual performance report by the Chief Financial Officer prior to submission for audit purposes. | Development of SDBIP process plan Issue SDBIP template to all Directors Conduct a session per Directorate for SDBIP development Directors should declare/sign off the information provided in the SDBIP Consolidate information received into a draft SDBIP | 17/01/2020 | 30/04/2020 | Manager: PMS | Rikhotso MJ
52 | AOPO - Differences noted between reported achievements and schedules and other portfolio of evidence documents. | Predetermined objectives | COMAF 39 | Contrary to the above requirement, during the audit of performance information, it was noted that the following performance indicator's reported achievements did not agree with achievement as per schedules and other portfolio of evidence documents. | New | Prepare regular, accurate and complete financial and performance reports that are supported and evidenced by reliable information. | Development and circulation of time schedule for submission of relevant POE's. Request Information Technology unit to insert auto reminder 3days prior the submission of perfomance report and POE's Development of a checklist by each department on submission of POE's,that will ensure alignment of each programme on the SDBIP with the actual POE's Internal Audit to review perfomamnce management reports | 17/01/2020 | 30/04/2020 | Manager: PMS | Rikhotso MJ
53 | SCM - Abuse of the SCM system: Cover Quoting | Procurement and Contract Management | COMAF 34 | Upon careful inspection of the supporting documents for the supply of bus transportation, three quotations were received from Hanani construction & projects (Pty) Ltd, PJ Thwala' s Lux Tours, MRC Transport & tours services (Pty) ltd and the following was noted: - The director of Hanani construction & projects (winning supplier) and the director of MRC Transport & tours services (Pty) ltd (Losing supplier) is both the same person (Makhosani Richard Chauke) which indicates that the suppliers fall within the same group of companies. - The address for Hanani construction & projects and MRC Transport & tours services (Pty) ltd is the same. This can either be due to the fact that SCM officials are not adequately trained to be able to identify such instances of cover quoting or possible collusion by officials with such suppliers. Furthermore, inadequate review of supporting documents by management prior to approval of quotations and purchase orders. This results in a SCM process that is not equitable, competitive and transparent. Furthermore, this could also constitute possible fraud within the SCM department. | New | The CFO did not review and monitor compliance with applicable laws and regulations in SCM. | Supply Chain Practitioners need to be trained on the roles and responsibilities. Notify National Treasury to add defaulted suppliers on the database of restricted suppliers for cover quoting. | 17/01/2020 | 30/04/2020 | Maluleke GP | Manager Supply Chain Management
54 | SCM - Suppliers in service of the state | Procurement and Contract Management | COMAF 34 | Contrary to the above, the following service providers were in service of the state at the time the award was granted. | Recurring | Failure to comply with the municipal supply chain management regulations as a result of inappropriate oversight over controls and compliance monitoring to supply chain management prescripts. | Notify National Treasury to add defaulted suppliers on the database of restricted suppliers | 17/01/2020 | 30/04/2020 | Maluleke GP | Manager Supply Chain Management
55 | SCM - Incomplete supplier declaration of interest | Procurement and Contract Management | COMAF 34 | During the audit we noted the following declarations of interest were incomplete as service providers did not disclose the individuals who have interest in their businesses and also under service of the Greater Giyani Municipality. | Recurring | Failure to comply with the municipal supply chain management regulations as a result of inappropriate oversight over controls and compliance monitoring to supply chain management prescripts. | Notify National Treasury to add defaulted suppliers on the database of restricted suppliers | 17/01/2020 | 30/04/2020 | Maluleke GP | Manager Supply Chain Management
56 | Contract management - Performance of the suppliers is not monitored and appropriate steps are not taken to address non-performance. | Procurement and Contract Management | COMAF 57 | GCC (2010) clause 22.1 states that Subject to GCC Clause 25, if the supplier fails to deliver any or all of the goods or to perform the services within the period(s) specified in the contract, the purchaser shall, without prejudice to its other remedies under the contract, deduct from the contract price, as a penalty, a sum calculated on the delivered price of the delayed goods or unperformed services using the current prime interest rate calculated for each day of the delay until actual delivery or performance. The purchaser may also consider termination of the contract pursuant to GCC Clause 23. GCC (2010) clause 23.1 (a) and (b) states that the purchaser, without prejudice to any other remedy for breach of contract, by written notice of default sent to the supplier, may terminate this contract in whole or in part: (a) if the supplier fails to deliver any or all of the goods within the period(s) specified in the contract, or within any extension thereof granted by the purchaser pursuant to GCC Clause 21.2; (b) if the Supplier fails to perform any other obligation(s) under the contract; or MFMA sec 116(3)(a) states that "A contract or agreement procured through the supply chain management policy of the municipality or municipal entity may be amended by the parties, but only after – 1. The reasons for the proposed amendment have been tabled in the council of the municipality or, in the case of a municipal entity, in the council of its parent municipality." 1. Tendered price for the following supplier is not documented in the bidding documents: • MY GRANNY GENERAL TRADING JV WANGA POWER PROJECTS - Makosha Access Road Upgrading from Gravel to Paving 2. The contract price for the following project is not documented in the contract • MOD HOPE - GENERAL VALUATION ROLL 3. Measures to monitor contract performance and delivery have been defined but have not been implemented. Based on the performance rating we have noted that the performance measures and methods used are not sufficient to ensure effective contract management. If they were effective the municipality would have noticed earlier that the following providers were underperforming. • MY GRANNY GENERAL TRADING JV WANGA POWER PROJECTS - Makosha Access Road Upgrading from Gravel to Paving • MHONYINI TRADING ENTERPRISE - HOMU 14 B TO 14 A UPGRADING FROM GRAVEL TO TAR • MULALO CONSULTING - MAGEVA SPORT CENTRE - TURNKEY G/G/M/015/038/2015 • Technicrete ISG (Pty) Ltd - Makosha Upgrading from Gravel to Paving – 80201865 • AES CONSULTING - Electrification of Villages 4. No specification of administration reference book in the following contracts. • CCG Systems • AES CONSULTING - Electrification of Villages 5. The end date is not stipulated in the following contract. • MOD HOPE - GENERAL VALUATION ROLL 6. The reasons for the following contract extensions were not tabled in the council of the municipality. • MY GRANNY GENERAL TRADING JV WANGA POWER PROJECTS - Makosha Access Road Upgrading from Gravel to Paving • Marungane Projects - Electrification of Mbaula village - 80203001 • AES CONSULTING - Electrification of Villages | Recurring | Management did not effectively manage the projects to ensure that services are delivered in accordance with the contract | If the supplier fails to deliver any or all of the goods or to perform the services within the period(s) specified in the contract, the purchaser shall, without prejudice to its other remedies under the contract, the following should apply: - deduct from the contract price, as a penalty - terminate the contract in whole or in part: > if the supplier fails to deliver any or all of the goods within the period(s) specified in the contract, > if the supplier fails to perform any other obligation(s) under the contract; or >if the supplier, in the judgement of the purchaser, has engaged in corrupt or fraudulent practices in competing for or in executing the contract. - The purchaser, without prejudice to any other remedy for breach of contract, by written notice of default sent to the supplier, - In the event the purchaser terminates the contract in whole or in part, the purchaser may procure, upon such terms and in such manner, as it deems appropriate, goods, works or services similar to those undelivered, and the supplier shall be liable to the purchaser for any excess costs for such similar goods, works or services. However, the supplier shall continue performance of the contract to the extent not terminated. - Where the purchaser terminates the contract in whole or in part, the purchaser may decide to impose a restriction penalty on the supplier by prohibiting such supplier from doing business with the public sector for a period not exceeding 10 years. | 17/01/2020 | 30/04/2020 | Maluleke GP Mahani NT | Manager Supply Chain Management Manager PMU
57 | Contract management - limitation | Procurement and Contract Management | COMAF 58 | Contract amendment of the following contract was not submitted for audit purposes. AES CONSULTING - Electrification of Villages | New | Management did not implement proper record keeping in a timely manner to ensure that complete, information is accessible and available to submit for audit purposes. | Information was subsequently provided to AGSA and Magement believes that the finding is resolved. The matter has been reffered back to AGSA |  |  | Maluleke GP | Manager Supply Chain Management
58 | Use of management expert: Provision for rehabilitation of landfill site (Limitation of scope) | Provisions | Comaf 4 | During the audit of provision for rehabilitation of landfill site the following were identified: The report provided by management on the provision for rehabilitation of landfill site does not provide comprehensive details of the calculation. That is, it does not provide the following amongst others: 1. The method used in mathematical computation of the provision. 2. The assumptions used in making/computing the provision. 3. The source of the data used in calculating the provision. 4. The variables used in the calculation and their financial impact on the provision. 5. The period covered by the provision calculation. 6. The discount rate used in calculating the net present value of the provision. 7. The limitations of the data used if there were any encountered. 8. The detailed mathematical computation of the provision amount. 9. Time value of money. Furthermore, we noted that the amount R25 700 366.00 as on the face of the financial statements and disclosed in note 17 to the financial statements does not agree with the amounts as per the report prepared by the management expert, ie 4E Consulting (Pty) Ltd. The amount of R25 700 366.00 does not meet the requirements of GRAP 19 to be recognised as a provision and as a result we were unable to determine how management had arrived at this amount. This has resulted in scope limitation on our work. | Recurring | Lack of review of the work performed by the management expert by the Chief Financial Officer. | Comprehensive report for the provision for the landfill site was subsequently submitted and accepted for audit purposes by AGSA. Similar template will be used to calculate the future provision of the landfill site. | 17/01/2020 | 30/04/2020 | Mhangwana D | CFO
59 | Provision for landfill site - No accounting policy for provision of rehabilitation of landfill site | Provisions | Comaf 4 | During the audit of provisions we have noted that the Municipality has a landfill site that it must rehabilitate upon closure, however there was no specific accounting policy as to how the landfill site provision was determined. This could result in incorrect basis being used and wrong conclusions reached in determining the provision amount to be recognised. We are also unable to conclude on fair presentation of the provision for land fill site disclosed in the financial statement. | New | Financial statements were not properly reviewed by the accounting officer to ensure that there is an accounting policy for all the material line items in the financial statements. | Deliverables in the SLA for independent reviewer should at least include but not limited to the following: 1. Alignment of Council approved policties against AFS policies and GRAP standards. 2. Ensure that all presentations and disclosures as requred by GRAP are adhered to 3. Submission of formal report upon conclusion of the review. | 17/01/2020 | 30/04/2020 | Mhangwana D | CFO
60 | Provision for landfill site - Provision not accuarately disclosed as per GRAP 19 | Provisions |  | During the audit of provision for we have noted that disclosure was not made as per requirements of paragraphs 98 and 99 of GRAP 19. The disclosure did not include the following - description of the nature of the obligation - the expected timing of any resulting outflows of economic benefits - an indication of the uncertainties about the amount or timing of those outflows. - the major assumptions made concerning future events - the increase during the period in the discounted amount arising from the passage of time This will result in non-compliance with GRAP 19, resulting in disclosure for provision of landfill site not being accurate and complete. | New | The accounting officer did not properly review the financial statements to ensure that appropriate and complete disclosure are made as per the requirements of GRAP. | The annual financial statement should be reconciled against trial balance, general ledger and the following supporting schedules (i) Asset register,operating lease register and finance lease register (ii)Payable age analysis (iii)Commitmnet register (iv)Receivable age analysis (v)Retention register (vi)Acrual listing (vii)Investment register (viii)Grant register (ix)Schedules of provisions (Actuarial report, Leave bonus, landfill site, Impairment, Long service, cost employment benefit, Workmen’s compensation (iix)Unauthorised ,irregular and fruitless and wastefull expenditure (Including MPAC recomendations) (x) A reconciliation between the budget and trial balance All reconciliations should be reviewed and signed off by the CFO | 17/01/2020 | 30/04/2020 | Mhangwana D | CFO
61 | Indigent debtors’ applications was not adequately completed but was approved by the municipality | Receivables | Comaf 35 | We noted that the application form for subsidy for member of the community listed hereunder who was declared ‘indigent’ was not adequately completed. In addition, we noted that even though the affidavit was attached, It was not authenticated/certified by the commissioner of oaths. Furthermore, the approved application forms for the below listed indigents customers could not be found in the indigents register resulting in the register being incomplete. | New | Revenue manager did not adequately review the indigent debtors’ applications before approval to ensure they comply with the municipal policy. | Request Corporate services to advertise. by 29. 02. 2020 and fill the budgeted indigent clerk position. Conduct a second review of all indigent applications before approval on the system Indigent verification should be conducted: - Agree system with the indigent register - Indigent on the system should be supported with relevant indigent applications. | 17/01/2020 | 30/04/2020 | Muhlari N | Manager Revenue
62 | Customers are not billed for services they receive from the municipality. | Receivables | Comaf 35 | During the audit of service charges, we noted that customers were not charged for the services on their statements. As a result, we could not confirm whether properties were billed for services rendered for the year under review. Furthermore, we noted as we traced from the age analysis to the customer statements, that the services for waste management were not charged on the statements. These properties for which the accounts belong to are being declared vacant hence, the amounts sitting in the age analysis. This has resulted in result in understatement of property rates, waste management and related receivables. The projected misstatements could me material | New | Management did not adequately review the property transfers against the system to ensure that all properties owned are added on the system for monthly billings. | Issue 1 Indigent verification should be conducted: - Agree system with the indigent register - Indigent on the system should be supported with relevant indigent applications. Issue 2 Put the accounts on hold Propose an adjustment for on hold balances. Delete on hold accounts if the system allows | 17/01/2020 | 30/04/2020 | Muhlari N | Manager Revenue
63 | Receivables - Debt impairment disclosed in Note 34 of AFS does not agree to the recalculated movement | Receivables | COMAF 56 | During the audit of receivables, we noted that the opening balance of the reconciliation for the provision for impairment as per note 11 to financial statements is misstated. | New | The CFO did not properly review the financial statements prior to submission for audit purposes. | The annual financial statement should be reconciled against trial balance, general ledger and the following supporting schedules (i) Asset register,operating lease register and finance lease register (ii)Payable age analysis (iii)Commitmnet register (iv)Receivable age analysis (v)Retention register (vi)Acrual listing (vii)Investment register (viii)Grant register (ix)Schedules of provisions (Actuarial report, Leave bonus, landfill site, Impairment, Long service, cost employment benefit, Workmen’s compensation (iix)Unauthorised ,irregular and fruitless and wastefull expenditure (Including MPAC recomendations) (x) A reconciliation between the budget and trial balance All reconciliations should be reviewed and signed off by the CFO | 17/01/2020 | 30/06/2020 | Muhlari N | Manager Revenue
64 | Receivables - Notice for discontinuance of services is not issued for accounts with balances older than 90 days. | Receivables | Comaf 38 | Contrary to the stipulations, we noted that services for accounts with balances older than 90 days were not discontinued as consumers were not issued with notices/reminders regarding services rendered by the municipality but not paid for. The discrepancies identified are as a result of weak internal controls that are in place. | Recurring | Non adherence of applicable laws and regulations by the Revenue Manager. | Prepare a debtors master file for long outstanding debtors and perform the following; Issuing of letters of demand to defaulters Non responsive debtors should be handed over to debt collectors | 17/01/2020 | 30/04/2020 | Muhlari N | Manager Revenue
65 | Receivables: Debtors’ applications were considered indigents before approval by the municipality | Receivables | COMAF 50 | During the audit of new applications to be registered as indigent debtors, we noted that the following applications were not approved by the municipality but were considered indigents prior to approval. The councillor who approves the applications on behalf of the municipality has acknowledged through the letter dated 2019/11/05 that the following customers who were considered indigents and whose applications were made during January, February and March 2019 were approved after year end, i.e. 30 September 2019. | New | Revenue Manager did not adequately review the indigent debtors’ applications prior to approval to ensure they comply with the policy. | Request Corporate services to advertise. by 29. 02. 2020 and fill the budgeted indigent clerk position. Conduct a second review of all indigent applications before approval on the system Indigent verification should be conducted: - Agree system with the indigent register - Indigent on the system should be supported with relevant indigent applications. | 17/01/2020 | 30/04/2020 | Muhlari N | Manager Revenue
66 | Receivables : Properties does not exist on the valuation roll and the customers that are billed on the customer statements are different to the customers registered on the valuation roll Furthermore, the details did not agree as the customers in the age analysis are not the registered owner in the valuation roll. | Receivables | COMAF 50 | During the audit of consumer debtors, we noted that details as in the age analysis do not agree to the valuation roll as we could found the erf numbers in the valuation roll. | New | Revenue Manager did not appropriately review the valuation roll to confirm the existence of consumer debtors. | Put the accounts on hold Propose an adjustment for on hold balances and delete on hold accounts if the system allows | 17/01/2020 | 30/04/2020 | Muhlari N | Manager Revenue
67 | Receivables - Opening balance of the reconcilliation for the provision for impairment as per AFS is mistated | Receivables | COMAF 56 | During the audit of receivables, we noted that the opening balance of the reconciliation for the provision for impairment as per note 11 to financial statements is misstated. | New | The CFO did not properly review the financial statements prior to submission for audit purposes. | The annual financial statement should be reconciled against trial balance, general ledger and the following supporting schedules (i) Asset register,operating lease register and finance lease register (ii)Payable age analysis (iii)Commitmnet register (iv)Receivable age analysis (v)Retention register (vi)Acrual listing (vii)Investment register (viii)Grant register (ix)Schedules of provisions (Actuarial report, Leave bonus, landfill site, Impairment, Long service, cost employment benefit, Workmen’s compensation (iix)Unauthorised ,irregular and fruitless and wastefull expenditure (Including MPAC recomendations) (x) A reconciliation between the budget and trial balance All reconciliations should be reviewed and signed off by the CFO | 17/01/2020 | 30/06/2020 | Muhlari N | Manager Revenue
68 | Receivables: Indigent debtors’ applications were not adequately completed but were approved by the municipality | Receivables | COMAF 43 | We noted that the application form for subsidy for member of the community listed hereunder who was declared ‘indigent’ was not adequately completed. In addition, we noted that even though the affidavit was attached, It was not authenticated/certified by the commissioner of oaths. Furthermore, the approved application forms for the below listed indigents customers could not be found in the indigents register resulting in the register being incomplete | New | Revenue manager did not adequately review the indigent debtors’ applications before approval to ensure they comply with the municipal policy. | Request Corporate services to advertise the budgeted indigent clerk position by 29. 02. 2020 and ensure that the position is filled. Conduct a second review of all indigent applications before approval on the system Indigent verification should be conducted: - Agree system with the indigent register - Indigent on the system should be supported with relevant indigent applications. | 17/01/2020 | 30/04/2020 | Muhlari N | Manager Revenue
69 | Statement of change in equity not correctly disclosed relating to prior period error | Reserves | Comaf 14 | During the audit of prior period notes and the statement of changes in net assets we noted that the notes does not cast as it includes the 13205978 twice, as it forms part of adjustment made in the Deficit for the year and the correction of errors of R 2207274 | Recurring | Lack of proper review of the annual financial statements by the Chief Financial Officer prior to submission to ensure that they are in compliance with GRAP. | The annual financial statement should be reconciled against trial balance, general ledger and the following supporting schedules (i) Asset register,operating lease register and finance lease register (ii)Payable age analysis (iii)Commitmnet register (iv)Receivable age analysis (v)Retention register (vi)Acrual listing (vii)Investment register (viii)Grant register (ix)Schedules of provisions (Actuarial report, Leave bonus, landfill site, Impairment, Long service, cost employment benefit, Workmen’s compensation (iix)Unauthorised ,irregular and fruitless and wastefull expenditure (Including MPAC recomendations) (x) A reconciliation between the budget and trial balance All reconciliations should be reviewed and signed off by the CFO | 17/01/2020 | 30/06/2020 | Mhangwana D | CFO
70 | Revenue from exchange transactions misstated by R318 630. | Revenue | Comaf 5 | Although the financial statements were reviewed on different levels including the consultants who are being paid by the municipality, it is not clear as to how the misstatement could not have been identified/detected prior to submission of the financial statements for audit purposes. | New | Lack of proper review of the annual financial statements by the Chief Financial Officer prior to submission for audit purposes. | The annual financial statement should be reconciled against trial balance, general ledger and the following supporting schedules (i) Asset register,operating lease register and finance lease register (ii)Payable age analysis (iii)Commitmnet register (iv)Receivable age analysis (v)Retention register (vi)Acrual listing (vii)Investment register (viii)Grant register (ix)Schedules of provisions (Actuarial report, Leave bonus, landfill site, Impairment, Long service, cost employment benefit, Workmen’s compensation (iix)Unauthorised ,irregular and fruitless and wastefull expenditure (Including MPAC recomendations) (x) A reconciliation between the budget and trial balance All reconciliations should be reviewed and signed off by the CFO | 17/01/2020 | 30/06/2020 | Mhangwana D | CFO
71 | Revenue - Overstatement of interest revenue: - R181 514.83 | Revenue | Comaf 17 | During the audit of revenue from exchange transactions (interest from investments), we noted that Some items that do not actually relate to interest but were included in the interest account resulting in misstatements | New | Prepare regular, accurate and complete financial and performance reports that are supported and evidenced by reliable information. | Enforce a system based segregation of duties in relation to capturing, reviewing and processing of journals (Only Managers can process journals in the system) | 17/01/2020 | 30/04/2020 | Muhlari N | Manager Revenue
72 | Revenue from exchange transactions misstated by R318 630.00 | Revenue | Comaf 5 | Although the financial statements were reviewed on different levels including the consultants who are being paid by the municipality, it is not clear as to how the misstatement could not have been identified/detected prior to submission of the financial statements for audit purposes. | New | Lack of proper review of the annual financial statements by the Chief Financial Officer prior to submission for audit purposes. | The annual financial statement should be reconciled against trial balance, general ledger and the following supporting schedules (i) Asset register,operating lease register and finance lease register (ii)Payable age analysis (iii)Commitmnet register (iv)Receivable age analysis (v)Retention register (vi)Acrual listing (vii)Investment register (viii)Grant register (ix)Schedules of provisions (Actuarial report, Leave bonus, landfill site, Impairment, Long service, cost employment benefit, Workmen’s compensation (iix)Unauthorised ,irregular and fruitless and wastefull expenditure (Including MPAC recomendations) (x) A reconciliation between the budget and trial balance All reconciliations should be reviewed and signed off by the CFO | 17/01/2020 | 30/06/2020 | Muhlari N | Manager Revenue
73 | Payables - Understatement of LGSETA grant | Budget | Comaf 30 | During the audit of government grants and subsidies (revenue from non-exchange transactions) (interest from investments) it was noted that the grant amount for LGSETA as per the grant register and bank statements does not agree to the amount in note 28 in the AFS | New | Revenue and budget manager did not ensure the figures on the AFS are reflecting information on the supporting documents. | The annual financial statement should be reconciled against trial balance, general ledger and the following supporting schedules (i) Asset register,operating lease register and finance lease register (ii)Payable age analysis (iii)Commitmnet register (iv)Receivable age analysis (v)Retention register (vi)Acrual listing (vii)Investment register (viii)Grant register (ix)Schedules of provisions (Actuarial report, Leave bonus, landfill site, Impairment, Long service, cost employment benefit, Workmen’s compensation (iix)Unauthorised ,irregular and fruitless and wastefull expenditure (Including MPAC recomendations) (x) A reconciliation between the budget and trial balance All reconciliations should be reviewed and signed off by the CFO | 17/01/2020 | 30/06/2020 | Muhlari N | Manager Revenue
74 | Misstatements identified in remuneration of key management personnel: (R373 900.67) | Financial findings matters | Comaf 22 | We noted during the audit that the amounts for remuneration of key management personnel as disclosed in note 29 to the financial statements has been misstated as a result of inaccurate figures been used. Although the financial statements were reviewed on different levels including the consultants who are being paid the municipality, it is not clear as to how the misstatement could not have been identified/detected prior to submission of the financial statements for audit purposes. | New | Lack of proper review of the annual financial statements by the Chief Financial Officer prior to submission for audit purposes. | The annual financial statement should be reconciled against trial balance, general ledger and the following supporting schedules (i) Asset register,operating lease register and finance lease register (ii)Payable age analysis (iii)Commitmnet register (iv)Receivable age analysis (v)Retention register (vi)Acrual listing (vii)Investment register (viii)Grant register (ix)Schedules of provisions (Actuarial report, Leave bonus, landfill site, Impairment, Long service, cost employment benefit, Workmen’s compensation (iix)Unauthorised ,irregular and fruitless and wastefull expenditure (Including MPAC recomendations) (x) A reconciliation between the budget and trial balance All reconciliations should be reviewed and signed off by the CFO | 17/01/2020 | 30/06/2020 | Shivambu J | Manager Expenditure
75 | Expenditure: fuel and oil - misstatements: R1 075 624.00 | Operating expenditure | COMAF 2 | During the audit planning for expenditure, we noted that the amount as disclosed in note 37 to the financial statements relating to fuel and oil does not agree to the amount as per trail balance resulting in misstatements. | New | Lack of proper review of the annual financial statements by the Chief Financial Officer prior to submission for audit purposes. | The annual financial statement should be reconciled against trial balance, general ledger and the following supporting schedules (i) Asset register,operating lease register and finance lease register (ii)Payable age analysis (iii)Commitmnet register (iv)Receivable age analysis (v)Retention register (vi)Acrual listing (vii)Investment register (viii)Grant register (ix)Schedules of provisions (Actuarial report, Leave bonus, landfill site, Impairment, Long service, cost employment benefit, Workmen’s compensation (iix)Unauthorised ,irregular and fruitless and wastefull expenditure (Including MPAC recomendations) (x) A reconciliation between the budget and trial balance All reconciliations should be reviewed and signed off by the CFO | 17/01/2020 | 30/06/2020 | Shivambu J | Manager Expenditure