## COVER PAGE
4TH QUARTER SDBIP REPORT

## TABLE OF CONTENT
TABLE OF CONTENT
1. Introduction and Legislation
2. Acronyms and Abbreviations
3. Vison, Mission and Strategic Map
4. Departments
5. Institutional Performance
4. HIGHER LEVEL SDBIP
4.1. Spatial Rational
4.2. Municipal Transformation and Organisational Development
4.3. Basic Service Delivery
4.4. Local Economic Development
4.5. Municipal Finance Management and Viability
4.6. Good Governance and Public Participation
5. LOWER LEVEL SDBIP
5.1. Spatial Rational
5.2. Municipal Transformation and Organisational Development
5.3. Baisc service Delivery
5.4. Local Economic Development
5.5. Municipal Finance Management and Viability
5.6. Good Governance and Public Participation
6. Monthly Revenue and Expenditure
7. Monthly Revenue and Expenditure by Vote
8. Capital Cashflow
9. Capital Cashflow by Vote
10. Approval By The Mayor

## INTRO AND LEGISLATION
Summary and Legislation
This report serves as the First Quarter Institutional Performance Report for the 2018/2019 financial year ending September 2018. It provides feedback on the performance level achieved against the targets as laid out in the IDP and SDBIP Scorecards. In the case of under-performance, the respective concerns or mitigating reasons are highlighted and detail pertaining to the relevant measures taken to address these challenges are included thereto. The overall performance for the Greater Giyani Municipality is based on a composite Performance Scorecard of each Department comprising of all indicators and projects inclusive of the IDP and SDBIP.
Section 40 of the MSA states that a municipality must establish mechanisms to monitor and review its performance management system. The First Quarter SDBIP report is prepared in terms of Section 52 (d) of the Municipal Financial Management Act

## ACRONYMS & ABBREVIATIONS
ACRONYMS AND ABBREVIATIONS
AG | Auditor General
GGM | Greater Giyani Municipality
MDM | Mopani District Municipality
CWP | Community Works Programme
DMP | Disaster Management Plan
DoE | Department of Energy
DoHS | Department of Human Settlement
EMP | Environmental Management Plan
EPWP | Expanded Public Works Programme
FBW | Free Basic Water
IDP | Intergrated Development Plan
IGR | Inter Governmental Relations
LED | Local Economic Development
MFMA | Municipal Finance Management Act
MIG | Municipal Infrastructure Grant
MM | Municipal Manager
MPAC | Municipal Public Account Committee
MSIG | Municipal Systems Improvement Grant
N/A | Not Applicable
SLA | Service Level Agreement
PIA | Project Implementing Agent
PMS | Perfomance Management System
PMU | Project Mnagement Unit
SCM | Supply Chain Management
SLP | Social and Labour Plan
SDBIP | Service Delivery and Budget Implementation Plan
WAC | Ward AIDS council

## VIS MISS STRA MAP
VISION, MISSION AND STRATEGIC MAP
VISION, MISSION AND STRATEGIC MAP The Vision of Greater Giyani Municipality is: A Municipality where environmental sustainbility, tourism and agriculture thrive for economic growth. The Mission of Greater Giyani Municipality is: Ademocratic accountable municipality that ensure the provision of services through sound environment management practices, local economic development and community participation. Greater Giyani Muncipality has identified 6 Strategic Objectives which are contained in the Intergrated Development Plan. All municipal programmes will be aligned to the objectives outlined in the figure below:
Strategic Objectives
To develop and retain the best human capital, effective and efficient administrative and operational support systems
To develop sustainable infrastructure networks which promotes economic growth and improve quality of life
To create an enabling environment for sustainable economic growth
To improve financial management systems to enhance vanue base
To develop governance structures and systems that will ensure effective public consultation and organizational discipline
To develop an effective spatial framework that promotes integrated and sustainable development

## DEPARTMENT
Greater Giyani Municipality administration is composed of the following departments: 1. Office of the Municipal Manager, 2. Corporate Services, 3.Strategic Planning and LED, 4. Budget and Treasury, 5. Technical Services, 6. Community Services
Municipal Manager | To lead, direct and manage a motivated and inspired Administration and account to the Greater Giyani Municipality Council as Accounting Officer for long term Municipal sustainability to achieve a good creditor rating within the requirements of the relevant legislation and whereas the following sections within the department, i.e. Performance Management, Risk Management and Internal Auditing is managed for integration, efficient, economic and effective communication and service delivery.
Finance | To secure sound and sustainable management of the financial affairs of Greater Giyani Municipality by managing the budget and treasury office and advising and if necessary assisting the accounting officer and other directors in their duties and delegateion contained in the MFMA. Ensuring that the Greater Giyani Municipality is 100% financially viable when it comes to Cost Coverage and to manage the Grant Revenue of the municipality so that no grant funding is foregone
Community Services | To coordinate Environmental Health Services, Libraries, Safety and Security, Environmental and Waste management Parks and Recreation as well as Disaster management to decrease community affected by disasters
Technical Services | To ensure that the service delivery requirements for roads are met and maintenance of water, sewerage and electricity are conducted for access to basic services as well as no less than an average of 100% MIG expenditure
Development and Planning | To direct the Greater Giyani Municipality’s resources for advanced economic development and investment growth through appropriate town and infrastructure planning in order that an environment is created whereby all residents will have a sustainable income
Corporate Services | To ensure efficient and effective operation of council services, human resources and management, legal services HIV/Aids, Youth, Disabled and Gender Desk Sports Arts and culture, Communication, Events and the provision of high quality customer orientated administrative systems. Ensuring 100% compliance to the Skills Development Plan

## INSTITUTIONAL PERFORMANCE
4th Quarter SDBIP Performance Analysis
The Municpality has a total of 87 Key Performance Indicators applicable for the quarter and were all assessed. All other KPI's are not applicable for reporting in this quarter.
All the assessed KPI’s and Projects contribute to the overall performance level of the SDBIP Scorecards as reflected in this report.
KPA1.
Saptial Rationale
Type | Total KPI’s Assessed | Targets Achieved | % Target Achieved | Targets NOT Achieved | % Target NOT Achieved
SDBIP | 10 | 2 | 20% | 8 | 80%
Total | 10 | 2 | 20% | 8 | 80%
Municipal Transformation and Organisational Development
Municipal Transformation and Organisational Development is responsible for 14 KPI's which 11 were eligible for assessment and 1 were not applicable for the quarter, statistics as follows:
Table 1: Institutional Development and Transformation Statistics
Type | Total KPI’s Assessed | Targets Achieved | % Target Achieved | Targets NOT Achieved | % Target NOT Achieved
SDBIP | 14 | 11 | 79% | 3 | 21%
Total | 14 | 11 | 79% | 3 | 21%
KPA 3.
Basic Service Delivery and Infrastructure Development
Basic Service Delivery and Infrastructure Development is responsible for 39 KPI's wich 27 were eligible for assessment and 12 were not applicable for the quarter, statistics as follows
Table 2: Basic Service Delivery and Infrastructure Development statistics
Type | Total KPI’s Assessed | Targets Achieved | % Target Achieved | Targets NOT Achieved | % Target NOT Achieved
SDBIP | 27 | 16 | 59% | 11 | 41%
Total | 27 | 16 | 59% | 11 | 41%
KPA4.
Local Econimic Development
Local Econimic Development was responsible for 4 KPI's which 3 were eligible for assessment and only 1 was not applicable for the quarter,statistics as follows:
Type | Total KPI’s Assessed | Targets Achieved | % Target Achieved | Targets NOT Achieved | % Target NOT Achieved
SDBIP | 4 | 3 | 100% | 0 | 0%
Total | 4 | 3 | 100% | 0 | 0%
KPA5
Municipal Financial Management and Viability
Municipal Financial Management and Viability is responsible for 10 KPI's which 8 were eligible for assessment which 2 were not applicable for the quarter
Type | Total KPI’s Assessed | Targets Achieved | % Target Achieved | Targets NOT Achieved | % Target NOT Achieved
SDBIP | 8 | 7 | 60% | 1 | 40%
Total | 8 | 7 | 60% | 1 | 40%
KPA6
Good Governance and Public Participation
Good Governance and Public Participation is responsible for 30 KPI's of which 24 were applicable for assessment and 6 were not applicable for the quarter,statistics as follows:
Type | Total KPI’s Assessed | Targets Achieved | % Target Achieved | Targets NOT Achieved | % Target NOT Achieved
SDBIP | 24 | 15 | 86% | 9 | 14%
Total | 24 | 15 | 86% | 9 | 14%
Overall KPA Analysis
KPA | Total Q1 SDBIP Indicators | Percentange per KPA
KPA 1: Spatial Rational | 10 | 59%
KPA 2: Institutional Development and Transformation | 14 | 79%
KPA 3: Infrastructure Development And Basic Services | 27 | 59%
KPA 4: Local Economic Development | 4 | 100%
KPA 5:Financial Viability | 8 | 60%
KPA 6:Public Participation And Good Governance | 24 | 86%
TOTAL | 87 | 62%
The overall Institutional performance score achieved for the 4th Quarter of 2018/2019, ending June 2019 was 62% which shows a regress as compared to the third quarter analysis

## HIGH LEVEL SDBIP
Priority Issue/Programme | Development Objective | Key perfomance Indicator | Baseline | Annual Targets | Project Name | Project/Indicator Description | Location | Ward | Funding Source | Budget 2018/19 | Adjusted Budget 2018/19 | 1st Q Target | 2nd Q Targets | 3rd Q Targets | 4th Q Targets | Actual Performance | Variance | Reason for Variance | Corrective Measures | Portfolio Of Evidence | Dept
4.1 SPATIAL RATIONAL
Spatial and Town Planning | Advance Spatial Planning | To review and align the SDF in lign with SPLUMA by 30 June 2019 | Approved Spatial Development Framework (SDF) | Review the SDF by 30 June 2019 | REVIEW OF SDF | Submission of the SDF to Council for Approval | Greater Giyani Municipality | Administration | Income | Operational | Operational | N/A | N/A | Anaysis of information | Anaysis of information | Target Achieved, Anaysis of information | None | None | None | SDF and Council Resolution | P & Dev
4.2. MUNICIPAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT (HIGHER SDBIP)
Council Services | To develop and retain the best human capital, effective and efficient administrative and operational support systems | # of Council Meetings convened by 30 June 2019 | 6 Council meetings held in 2017/18 | 6 Council Meetings coordinated and supported by 30 June 2019 | Council Meeting | Organize Council Meeting as per schedule | Greater Giyani Municipality | Administration | Income | Operational | Operational | 1 Council Meeting | 1 Council Meeting | 2 Council Meetings | 2 Council Meetings | Target Achieved,2 Council meeting coordinated on 26 April and 29 May 2019 | None | None | None | Notices of Invitations, Minutes, Attendance Register | CORP
Council Services | To develop and retain the best human capital, effective and efficient administrative and operational support systems | # of Executive Committee Meetings convened by 30 June 2019 | 10 Executive Committee held in 2017/18 | 12 Executive Committee Meetings to be coordinated and supported by 30 June 2019 | Executive Committee Meetings | Organize Executive Committee Meetings as per schedule | Greater Giyani Municipality | Administration | Income | Operational | Operational | 3 EXCO meetings | 3 EXCO meetings | 3 EXCO meetings | 3 EXCO meetings | Target Achieved, 3 EXCO meetings coordinated | None | None | None | Notices of Invitations, Minutes, Attendance register, | CORP
Council Services | To develop and retain the best human capital, effective and efficient administrative and operational support systems | # of Portfolio Committee Meetings to be held by 30 June 2019 | Approved Spatial Development Framework (SDF) | 96 Portfolio Committe Meetings (12 Per Portfolio Committee) by 30 June 2019 | Portfolio Committee Meetings | Organize Portfolio Committee meeting as per schedule | Greater Giyani Municipality | Administration | Income | Operational | Operational | 24 Portfolio Committe Meetings (3 per Portfolio Committee) coordinated | 24 Portfolio Committe Meetings (3 per Portfolio Committee) coordinated | 24 Portfolio Committe Meetings (3 per Portfolio Committee) coordinated | 24 Portfolio Committe Meetings (3 per Portfolio Committee) coordinated | Target not Achieved, 14 Portfolio Committe Meetings (3 per Portfolio Committee) coordinated | None | None | None | Notices of Invitations, Minutes, Attendance Register | CORP
Council Services | To develop and retain the best human capital, effective and efficient administrative and operational support systems | # of reports developed on implementation of council resolutions b 30 June 2019 | 4 reports developed in 2017/18 | 4 progress reports on implementation of council resolutions to be developed by 30 June 2019 | Council resolution implementation | Development of Council Resolution Register and monitor implementation of council resolutions | Greater Giyani Municipality | Administration | Income | Operational | Operational | 1 Council resolution implementation report | 1 Council resolution implementation report | 1 Council resolution implementation report | 1 Council resolution implementation report | Target Achieved, 2 Council resolution implementation report compiled | None | None | None | Proof of submissio and ATR | CORP
Human Resources and Organizational Development | To develop and retain the best human capital, effective and efficient administrative and operational support system | To Develop Work Skills Plan (WSP) and Annual Traning Report (ATR)and submit to LGSETA by 30 April 2019 | WSP and ATR submited on the 30 April 2019 | Develop and submit the WSP and ATR to LGSETA by 30 April 2019 | WSP and ATR | Development and submission of the WSP and ATR | Greater Giyani Municipality | Administration | Income | Operational | Operational | Implementation of the 2018/19 WSP | Implementation of the 2018/19 WSP | Conduct skills audit/introduce Gapskill webtool | Submit the WSP and ATR to LGSETA | Target Achieved, WPS and ATR reports submitted to LGSETA ON 30 April 2019. | None | None | None | WSP, ATR and Proof of Submission | CORP
Human Resources and Organizational Development | To develop and retain the best human capital , effective and efficient administrative and operational support system | To submit the Employment Equity report to Department of Labour (DoL) by 31 December 2018 | 2017/18 Employment Equity Report submitted | Submit Employment Equity Report DoL by 31 December 2018 | Equity | Development and submission of the Employment Equity Report | Greater Giyani Municipality | Administration | Income | Operational | Operational | Development of the Employment Equity Report | Submission of Annual Training Report | N/A | N/A | N/A | N/A | N/A | N/A | Employment Equity Report, Proof of Submission | CORP
4.3. BASIC SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT (HIGHER SDBIP)
Waste Magement | Accessible basic and infrastructure services | # of households with access to refuse removal | 63537 having access to refuse removal | Collect refuse removal to 18 564 households | Waste Management | Collection of waste in all the Townships in wards 11, 12, 13 & 21 | Section A, D1, D2, E, F and Kremetart | Wards 11, 12, 13 & 21 | Income | Operational | Operational | N/A | N/A | 18 564 of households with accses to refuse removal | 18 564 of households with accses to refuse removal | Target achieved | None | None | None | Proof of collection from the affected stakeholders. | MM& COM
Roads, Bridges and Storm water | Accessible basic and infrastructure services | # of km of roads tarred by 30 June 2019 | New Indicator | 14.2 km of roads to be tarred by 30 June 2019 | Upgrading of roads from gravel to tar | Upgrading of roads from gravel to tar | Giyani SectionE ,Giyani Section F,Homu 14 A,Makosha | 9,11,13, 14 | MIG | 17 840 006 | 41,752,658,00 | N/A | N/A | N/A | 14.2Km | Target not achieved |  |  |  | Certificate of completion | TECH
Waste Disposal Site | Accessible basic and infrastructure services | # of waste disposal site to be constructed by 30 June 2019 | New Indicator | 1 Waste Disposal Site Constructed by 30 June 2019 | 1 Waste Disposal site to be constructed | Planning and construction of waste disposal site | Dzingidzingi village |  | MIG and Income | 16468083 | 1,000,000, | N/A | N/A | Excavation for Cell 1 of waste disposal site | Excavation for Cell 1 of waste disposal site | Target Not Achieved | Excavation for Cell 1 of waste disposal site | Contractor has terminitated himself from the from the project. | GGM To appoint a new contractor to finish up the project. | Project progress report, handover certificate | TECH
Building and Construction | Accessible basic and infrastructure services | T o construct Municipal building at Civic Centre Phase 2 by 30 June 2019 | Phase 1 Completed | Construction of Civic Centre Phase 2 by 30 June 2019 | Civic Centre Building ,Phase 2 | Construction of Civic centre | Giyani | CBD | LGES | 4000000 | 8'000,000 | Tender Stage and Appointment of Contractor | Site Handover and establishment | Installation of HVAC; Electrical works; ICT equipment and Fire Control system and furniture | Practical Completion, Release First Retention | Target Not Achieved | Practical Completion, Release First Retention | late submision of the drawing on site. | Engineer to provide drawing to contractor in order for the works to proceed. | Certificate of completion | TECH
4.4. LOCAL ECONOMIC DEVELOPMENT (HIGHER SDBIP)
| To Create An Enabling Environment For Sustainable Economic Growth | # of jobs created through EPWP programme by 30 June 2019 | 150 jobs created | 200 Jobs to be created through CWP by 30 June 2019 | CWP | Jobs created through the implimentation of labour intensive methods | Giyani | All Wards | LGES | 500,000,00 | 500,000,00 | N/A | N/A | N/A | 200 jobs to be created through CWP | Target Achieved | None | None | None | Database of all people appointed in the program | P & Dev
| To Create An Enabling Environment For Sustainable Economic Growth | # of SMME's to be exposed to LED market by 30 June 2019 | 12 SMMEs exposed to LED market | 16 SMMEs exposed to led market by 30 June 2019 | Support to SMME's | SMMEs exposed to market by taking them along to different exhibition,tourism indaba,marula festival and rand show | Giyani | all wards | LGES | Operational | Operational | 4 SMMEs exposed to LED markets | 4 SMMEs exposed to LED markets | 4 SMMEs exposed to LED markets | 4 SMMEs exposed to LED markets | Target Achieved,3 SMME's exposed to Rand Show and 1 SMME exposed to Africa's Travel Indaba. | None | None | None | attandance register | P & Dev
4.5 MUNICIPAL FINANCE MANAGEMENT AND VIABILITY (HIGHER SDBIP
Budget and Reporting | To improve financial management systems to enhance venue base | Qualified Audit Opinion by 30 June 2019 | Qualified Audit Opinion | Qualified Audit Opinion by 30 June 2019 | Unqualified Audit Opinion | Complying with legislative frameworks, keeping records and submit AFS | Greater Giyani Municipality | Administration | Income | Operational | Operational | N/A | N/A | N/A | Obtaining of Unqualified Audit Opinion | Target not Achieved, Obtaining of Qualified Audit Opinion for 2017/2018 FY | None | None | None | AGSA Audit Report | B&T
Budget and Reporting | To improve financial management systems to enhance venue base | % MIG Budget spent by 30 June 2019 | 100% MIG budget spent | % MIG Budget spent by 30 June 2019 | MIG Spending | Spending 100 % of MIG allocated fund | Greater Giyani Municipality | Administration | MIG | 79 115 000 | 79 115 000 | % of MIG budget spent | % of MIG budget spent | % of MIG budget spent | % of MIG budget spent | Target not achieved, 95.01% of MIG budget spent | 4,9% (R2 969 141) | GGM was not in agreement with the service provider based on the dispute on some of the levels & installations of culverts | 2w22 | MIG Spending Report | B&T/
4.6 GOOD GOVERNANCE AND PUBLIC PARTICIPATION (HIGHER SDBIP)
Integrated Development Planning | To develop governance structures and systems that will ensure effective public consultation and organizational discipline | To review the IDP for 2017/2018 and development of 2018/19 IDP financial year by 31 May 2019 | IDP review for 2017/2018 was completed and approved by Council on the before 30 May 2018 | IDP review for 2017/2018 and development of 2018/19 IDP and approved by Council by 31 May 2019 | IDP Review | Compile IDP analysis phase, Organise the IDP rep forum. Conduct Strategic Planning session and present to the IDP rep forum, Draft IDP completed and submitted to Council for adoption by 31 March 2018, IDP Public participation, Final IDP submitted to council for adoption by 31 May 2018 | Greater Giyani Municipality | Administration | Income | 550'000'00 | 500'000'00 | Complete the IDP analysis phase and conduct the IDP representative forum. | Conduct Strategic Planning session and compile the IDP strategic chapter | Draft IDP completed and submitted to Council for adoption by 31 March 2019 | Final IDP submitted to council for adoption by 31 May 2019 | Target Achieved, Final IDP submitted to Council for adoption | None | None | None | Council resolutions, Draft IDP, Strategic plan report, Attendance register, Invitations for strategic plan, IDP Consultation attendance register, IDP Analysis phase | P& Dev
Performance Management | To develop governance structures and systems that will ensure effective public consultation and organizational discipline | To develop the SDBIP 2018/2019 and submit to the Mayor for signature within 28 days after approval of the budget by 30 June 2018 | SDBIP 2018/2019 was developed and submitted to the Mayor within 28 days after approval of the budget | Development and submission of the 2019/2020 SDBIP to the Mayor for signature within 28 days after approval of the budget by 30 June 2019 | SDBIP Development | Collect information from departments, Develop a draft SDBIP, Submit to departments for inputs, Incorporate inputs Submit to the Mayor for signature, Submit to council for noting. | Greater Giyani Municipality | Administration | Income | Operational | Operational | N/A | N/A | N/A | SDBIP signed by the Mayor within 28 days after approval of the budget | Target Achieved, Final SDBIP signed by the Mayor28 days after approval of the budget | None | None | None | Signed SDBIP | MM
Risk Management | To develop governance structures and systems that will ensure effective public consultation and organizational discipline | # of Fraud and Corruption awareness conducted by 30 June 2019 | New Indicator | 4 Fraud and Corruption awareness conducted | Risk Management project | Facilitate and coordinate risk management meetings | Greater Giyani Municipality | Administration | Income | Operational | Operational | submit quarterly attendance register for the fraud and corruption awareness conducted | submit quarterly attendance register for the fraud and corruption awareness conducted | submit quarterly attendance register for the fraud and corruption awareness conducted | submit quarterly attendance register for the fraud and corruption awareness conducted | Target achieved, | None | None | None | attendance register | MM
Risk Management | To develop governance structures and systems that will ensure effective public consultation and organizational discipline | # of risk management activities to be coordinated by 30 June 2019 | 4 risk activities were cordinated | 5 risk activities to be cordinated by 30 June 2019 | Risk Management project | Facilitate and coordinate risk management meetings | Greater Giyani Municipality | Aministration | Income | Operational | Operational | Submit Quarterly progress report | Submit Quarterly progress report | Submit Quarterly progress report | Develop Strategic Risk Register, Submit Quarterly progress report | Target Achieved,Strategic Risk Register, | None | None | None | Progress report and Attendance register | MM
Internal Auditing | To develop governance structures and systems that will ensure effective public consultation and organizational discipline | To develop the Internal Audit Charter, and Audit Committee Charter and submit to Audit Committee and council for approval by 30th June 2019 | Audit Committee Charter was developed and submitted to council for approval | Audit Committee Charter developed and submitted to Audit Committee(AC), and council for approval by 30 June 2019 | Audit Committee Charter | Audit Committee Charter submit to council for approval | Greater Giyani Municipality | Aministration | Income | Operational | Operational | N/A | N/A | N/A | Audit Committee Charter developed and submitted to AC, and to council for approval by 30th June 2019 | Target not Achieved,Audit Committee Charter developed and submitted to AC, and to council for approval not done | Audit Committee Charter developed and submitted to AC, and to council for approval by 30th June 2019 | Audit Committee meeting was rescheduled | full adherence to Audit Committee schedule | Approved Audit Committee Charter and Council Resolution | MM
Public Participation | To develop governance structures and systems that will ensure effective public consultation and organizational discipline | # of public participation to be conducted by 30 June 2019 | 4 public participation conducted | 4 public partcipatio to be conducted by 30 June 2019 | Public Participation | Consult members of the public on service delivery issues | Greater Giyani Municipality | All wards | Income | Operational | Operational | 1 public partcipatio to be conducted | 1 public partcipatio to be conducted | 1 public partcipatio to be conducted | 1 public partcipatio to be conducted | Target Achieved,9 public partcipatio to be conducted | None | None | None | Attendance register and Programme | CORP

## SPATIAL RATIONALE
Priority Issue/Programme | Development Objective | Key Perfomanace Indicator | Baseline | Annual Targets | Project Name | Project/Indicator Description | Location | Ward | Funding Source | Budget 2018/19 | Adjusted Budget | 1st Q Target | 2nd Q Targets | 3rd Q Targets | 4th Q Targets | Actual Performance | Variance | Reason for Variance | Corrective Measures | Portfolio Of Evidence | Dept
Spatial and Town Planning | To develop an effective spatial framework that promotes intergrtaed and sustainable devlopment | To develop the LUMS by 30 June 2019 | New Indicator | Development of lums BY 30 June 2019 | Alignment of LUS in BTO budget | Appointment of Service provider approval | Greater Giyani Municipality | All wards | Income | 500000 | 580,00 | Appointment of service provider | Data collection | Analysis phase | Analysis phase | Target Achieved, Analysis phase conducted | None | None | None | Council resolution,appointment letter of Service provider | P & Dev
Spatial and Town Planning | To develop an effective spatial framework that promotes intergrtaed and sustainable development | To expand town (Ngove village) by 30 June 2019 | New Indicator | Town Expansion (Ngove Village) by 30 June 2019 | Town Expansion (Ngove Village) | Township establishment | Ngove Village | Ward 21 | Income | 3 000 000 | 1 000 000 | Development of Specifications and Submit to BTO for Appointment of service provider | Expansion of Ngove Village | N/A | N/A | N/A | N/A | N/A | N/A | Specifications, Appointment Letter of Service Provider and title deed | P & Dev
Spatial and Town Planning | To develop an effective spatial framework that promotes intergrtaed and sustainable development | To establish Township at Siyandhani by 30 June 2019 | New Indicator | Approved layout plan by 30 June 2019 | Township establishment Siyandhani | Township establishment | Siyandhani village | Ward 07 | LGES | 500000 | 200000 | Appointment of service provider | Implementation | Implementation | approved layout plan | Target not Achived, approved layout plan not done | approved layout plan | Late appointment of Service Provider | Service Provider appointed | Layout plan | P & Dev
Spatial and Town Planning | To develop an effective spatial framework that promotes intergrtaed and sustainable development | Street naming( including registration) by 30 June 2019 | New Indicator | Registered street naming by 30 June 2019 | Street naming( including registration) | Street naming( including registration) | Giyani A,B,C,D,E and F | Ward 11,12,13 | LGES | 100000 | 0 | Appointment of service provider | Implementation | Implementation | registarted streets names | Target not Achieved, registarted streets names not conducted | Registarted streets names | Unavailability of community for Public Participation | Public participation conducted, street naming for section D will be done in the 2019/20 1st quarter | Registration | P & Dev
Spatial and Town Planning | To develop an effective spatial framework that promotes intergrtaed and sustainable development | Approved lay out plans by 30 June 2019 | New Indicator | To demarcate site at Skhunyane and Dzumeri villages by 30 June 2019 | Site Demarcation in villages | Township establishment | Greater Giyani Municipality | All wards | LGES | 1500000 | 1300000 | Appointment of service provider | Implementation | Implementation | approved layout plans | Target not Achieved,approved layout plans not done | approved layout plans | delay on environmental impact assessment outcome by LEDET | engage LEDET on environmental impact assessment outcome | Layout plan | P & Dev
Spatial and Town Planning | To develop an effective spatial framework that promotes intergrtaed and sustainable development | Approved lay out plans by 30 June 2019 | New Indicator | To formalise Church View by 30 June 2019 | Formalisation of Church View | Township establishment | section E | ward 11 | LGES | 650126 | 650126 | Appointment of service provider | Implementation | Implementation | approved lay out plans | Target not Achieved,approved layout plans not done | approved layout plans | delay on environmental impact assessment outcome by LEDET | engage LEDET on environmental impact assessment outcome | Layout plan | P & Dev
Spatial and Town Planning | To develop an effective spatial framework that promotes intergrtaed and sustainable development | Proclamation diagram and numbering by 30 June 2019 | New Indicator | Proclamation daigram and numbering by 30 June 2019 | Proclamation Programme | Proclamation Programme | Greater Giyani Municipality | ward 11,12,13 | LGES | 1000000 | 400000 | Appointment of service provider | Implementation | Implementation | proclamation diagram and number | Target not Achievd,proclamation diagram and numbering not done | proclamation diagram and number | Late appointment of Service Provider | Service Provider appointed | proclation diagram | P & Dev
Spatial and Town Planning | To develop an effective spatial framework that promotes intergrtaed and sustainable development | 539 tittle deeds by 30 June 2019 | New Indicator | Deeds registration of 539 Eren by 30 June 2019 | Deeds registration of sites | Deeds registration of sites | giyani section F | ward 13 | LGES | 800000 | 600000 | Appointment of service provider | Implementation | Implementation | 539 tittle deeds | Target not Achived, 539 tittle deeds submitted to CoGHSTA and awaiting approval | 539 tittle deeds | Late submission of tittle deeds | Tittle Deeds submitted to CoGHSTA on time | Main title deed | P & Dev
Spatial and Town Planning | To develop an effective spatial framework that promotes intergrtaed and sustainable development | Approved amended General Plan by 30 June 2019 | New Indicator | Approved amended General Plan by 30 June 2019 | Rezoning and subdivision of parks | Rezoning and subdivision of parks | giyani township | ward 11,12,13 | LGES | 500000 | 200,00 | Appointment of service provider | Implementation | Implementation | approved amended general plan | Target not Achieved,approved amended general plan not done | approved amended general plan | Late appointment of Service Provider | Service provider appointed and the general plan will be done in the 4th quarter | subdivision diagram | P & Dev
Spatial and Town Planning | To develop an effective spatial framework that promotes intergrtaed and sustainable development | Upgraded GIS System by 30 June 2019 | New Indicator | To upgrade GIS System by 30 June 2019 | GIS Upgrade | GIS Upgrade | N/A | All wards | LGES | 200000 | 0 | Appointment of service provider | Implementation | N/A | upgraded GIS System | Target not Achieved,Upgrading of GIS system | upgraded GIS System | Budget Constraints | to be budgeted for in the next financial year | GIS licence | P & Dev

## LMTOD
Priority Issue/Programme | Development Objective | Key Perfomamce Indicator | Baseline | Annual Target | Project Name | Project /Indicator Description | Location | Ward | Funding Source | Budget 2018/19 R'000 | Adjusted Budget R'000 | 1st Q Target | 2nd Q Targets | 3rd Q Targets | 4th Q Targets | Actual Performance | Variance | Reason for Variance | Corrective Measures | Portfolio Of Evidence | Dept
5.1. MUNICIPAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT (LOWER SDBIP)
Wellness Program | To develop and Retain the best Human Capital , Effective and Efficient Administrative and Operational Support System | To compile OHS reports on site inspection conducted by 30 June 2019 | 4 OHS reports on site | # of OHS on site inspection developed by 30 June 2019 | Occupational health | Development of 4 OHS reports | Greater Giyani Municipality | Adminstration | Income | 780731 | 780731 | 1 progress report on OHS | 1 progress report on OHS | 1 progress report on OHS | 1 progress report on OHS | Target Achieved,1 progress report on OHS compiled | None | None | None | OHS implementation report | CORP
Human Resources and Organizational Development | To develop and Retain the best Human Capital , Effective and Efficient Administrative and Operational Support System | To review HR policies Framework by 30 June 2019 | HR Policies reviewed | Review of the HR policies by 30 June 2019 | HR Policies | Reviewing of the HR Policies for levels | Greater Giyani Municipality | Adminstration | Income | Operational | Operational | N/A | Invite inputs from departments regarding the new HR policy | Submit the draft HR policies to Council for provisional approval. Consultation with organised labour | Submit the final Draft HR policies to Council for approval | Target Achieved,Thirty five (35) final draft policies submitted to Council for approval on 29 May 2019 | None | None | None | HR policies and Council Resolution | CORP
Human Resources and Organizational Development | To develop and Retain the best Human Capital , Effective and Efficient Administrative and Operational Support System | To review the Organogram by 30 June 2019 | Approved Organogram 2017/2018 | Reviewing of organizational structure by 30 June 2019 | Organogram review | Reviewing of organizational structure | Greater Giyani Municipality | Adminstration | Income | Operational | Operational | N/A | Invite inputs from departments regarding the new organogram | Submit the draft organogram to Council for inputs. Consultation with organised labour | Submit the final Draft Organogram to Council for approval | Target Achieved, draft organogram submitted to Council for approval on 29 May 2019 | None | None | None | Approved Oganogram and Council Resolution | CORP
Human Resources and Organizational Development | To develop and Retain the best Human Capital , Effective and Efficient Administrative and Operational Support System | Number of posts filled in terms of the approved priority list by 30 June 2019 | Approved Organogram 2017/2018 | 26 Post filled in terms of the organogram by 30 June 2019 | Personnel Recruitment | Personnel Recruitment as per priority list | Greater Giyani Municipality | Adminstration | Income | Operational | Operational | 4 positions to be filled | 6 positions to be filled | 8 positions to be filled | 8 positions to be filled | Target not Achieved,7 positions filled | 1 position to be filled | 1 interviewed and awaiting finalisation | to finalise the appointment | Advertisement, Shortlisting reports, Interview reports and Appointment letters | CORP
Informaton Technology | To develop and Retain the best Human Capital , Effective and Efficient Administrative and Operational Support System | To maintain network Infrastructure by 30 June 2019 | Network Infrasture maintainned | Maintanance of network Infrastructure by 30 June 2018 | Infrastructure Maintanance | Maintaning of the network infrastructure | Greater Giyani Municipality | Adminstration | Income | Operational | Operational | Maintanance of network Infrastructure | Maintanance of network Infrastructure | Maintanance of network Infrastructure | Maintanance of network Infrastructure | Target Achieved,Maintanance of network Infrastructure conducted | None | None | None | Maintanance Register | CORP
Informaton Technology | To develop and Retain the best Human Capital , Effective and Efficient Administrative and Operational Support System | % update of municipal website by 30 June 2019 | Website updated 100% in 2017/18 Financial Year | 100% updating of municipal website by 30 june 2019 | Update of Municipal website | Placing of compliance documents on municpal website | Greater Giyani Municipality | Adminstration | Income | Operational | Operational | 100% information sent to SITA to update the website | 100% information sent to SITA to update the website | 100% information sent to SITA to update the website | 100% information sent to SITA to update the website | Target Achieved, 100% information sent to SITA to update the website done | None | None | None | Sent Mail | CORP
Informaton Technology | To develop and Retain the best Human Capital , Effective and Efficient Administrative and Operational Support System | # of IT Steering Committee Meetings to be coordinated by 30 June 2019 | 4 meetings held in 2017/18 Financial year | 4 IT Steering Committee meetings to be coordinate by 30 June 2019 | IT Governance, Risks and Compliance | Coordination of the IT Steering Committee Meeeting | Greater Giyani Municipality | Adminstration | Income | Operational | Operational | 1 IT steering committee meetings coordinated | 1 IT steering committee meetings coordinated | 1 IT steering committee meetings coordinated | 1 IT steering committee meetings coordinated | Target Achieved,1 Steering Committee meeting held on 20 May 2019 | None | None | None | Attendance Registers and Minutes | CORP
Provisioning and supply of IT equipment | To develop and Retain the best Human Capital , Effective and Efficient Administrative and Operational Support System | # of payments for leased desktops and laptops to be Coordinated By 30 June 2019 | 57 desktops and 85 laptops | 4 payments for leased desktops and laptops to be coordinated By 30 June 2019 | Provisioning and supply of IT equipment | To provide IT Equipments | Greater Giyani Municipality | Adminstration | Income | 1 200 000 | 1 200 000 | 1 payments for leased desktops and laptops to be Coordinated | 1 payments for leased desktops and laptops to be Coordinated | 1 payments for leased desktops and laptops to be Coordinated | 1 payments for leased desktops and laptops to be Coordinated | Target Achieved, 1 payment coordinated for leased desktops and laptops | None | None | None | Invoices | CORP
Management of litigation | To develop and Retain the best Human Capital , Effective and Efficient Administrative and Operational Support System | # of litigation cases received and finalized by 30 June 2019 | 5 cases finalized | 15 litigation cases received and finalized by 30 June 2019 | Management of litigations | Attending and finalizing all litigation cases of the municipality | Greater Giyani Municipality | Adminstration | Income | 3 000 000 | 8 000 000 | # of litigation cases received and finalized by 30 June 2019 | # of litigation cases received and finalized by 30 June 2019 | 9 litigation cases received and finalized by 30 June 2019 | 6 litigation cases received and finalized by 30 June 2019 | Target not Achieved, | 6 litigation cases received arenot finalized |  |  | Litigation Register and Report | MM

## LBSD
5.2. BASIC SERVICE DELIVERY AND INFRASTRUCTURE DEVELOPMENT (LOWER SDBIP)
Priority Issue | Development Objective | Key Perfomance Indicator | Baseline | Annual Targets | Project Name | Project Description | Location | Ward | Funding Source | Budget 2018/19 R'000 | Adjusted Budget R'000 | 1st quarter | 2nd quarter | 3rd quarter | 4th Quarter | Actual Performance | Variance | Reason for Variance | Corrective Measures | Portfolio of Evidence | Dept
Electricity Provision | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life? | To connect 500 units at Mbaula villages by 30 June 2019 | 2447 units connected | Design of 500 units at Mbaula,to be connected with electricity by 30 June 2019 | Electrification of Mbaula,Mushiyani,,Xitlakati & Khaxani villages(1082) units) | Construction of Electrical Network Infrastructure | Mbaula | Ward 23 & 27 | INEP | 2000000 | 2000000 | Appointment of Consultants | Appointment of contractors at Mbaula village | Appointment of Consultants and contractors at Mbaula village | Complete MV and LV networks at Mbaula village | Target achieved,Completed MV and LV networks at Mbaula village | None | None | None | Appointment letters and progress report on the completion of the MV and LV networks | TECH
Electricity Provision | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life? | To connect 898 units at Shikhumba,Nkomo C, Nkomo B&Dzingidzingi Villages by 30 June 2019 | 3621 households connected | To connect 898 units at Shikhumba,Dzingidzingi and designs for,Nkomo C & Nkomo B Villages by 30 June 2019 | Electrification of Shikhumba,Nkomo C, Nkomo B & DzingidzingVillage(898 units) | Construction of Electrical Network Infrastructure | Shikhumba,Nkomo C, Nkomo B & Dzingidzingi | Ward 4 ,10 ,21 and 22 | INEP | 7 ,100,000 | 13'000'000 | Site handover, appointment of labour, Surveying of pole holes, excavating the pole holes, dresing and planting of poles, stringing of conductors | Complete MV and LV networks at Dzingidzingi and Shikhumba villages | Enegising of 898 units at Dzingidzingi and Shikhumba | Close out report | Target achieved,Close out report done | None | None | None | Certificate of Completion for Shikhumba and Dzingidzingi, Designs for Nkomo B and Nkomo C | TECH
Electricity Provision | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life? | 300 units at Sekhiming connected with elecricity by 30 June 2019 | 924 Households connected | 300 Households connected with electricity at sekhiming by 30 June 2019 | Electrification of Mhlava-Willem, Sekhiming, Mbatlo & Shivulani Village(300units) | Construction of Electrical Network Infrastructure | Mhlava-Willem, Sekhiming, Mbatlo & Shivulani Village( | Ward 16 ,8 and 20 | INEP | 2000000 | 3'200'000 | Site handover, appointment of labour, Surveying of pole holes, excavating the pole holes, dresing and planting of poles, stringing of conductors | Complete MV and LV networks at Sekhiming village | Enegising of 300 units at Sekhiming | Close out report | Target achieved,Close out report done | None | None | None | Certificate of Completion for Sekhiming, Designs for Mhlava-Willem and Mbatlo | TECH
Electricity Provision | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life? | To Connect electricity to 450 units at Mahlathi and Ximawusa Villages by 30 June 2019 | 2344 households connected | 450 units at Mahlathi and Ximawusa,connected with elecricity by 30 June 2019 | Electrification of ,Mahlathi and Ximawusa villages (591 units) | Electrification of 450 units at Mahlathi and Ximawusa Villages | Mahlathi ,Ximawusa | Ward 31, 3, 18 and 19 | INEP | 4100000 | 4'071'000 | Site handover, appointment of labour, Surveying of pole holes, excavating the pole holes, dresing and planting of poles, | Complete MV and LV networks at Sekhiming village | Complete MV and LV networks at Mahlathi and Ximawusa Villages | Connect and energise 450 units at Mahlathi and Ximawusa | Target achieved,Connect and energise 450 units at Mahlathi and Ximawusa | None | None | None | Certificate of Completion for Mahlathi and Ximawusa | TECH
Electricity Provision | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life? | To upgrade Giyani traffic lights from solar to electricity and R81 lighting by 30 June 2019 | New Indicator | To upgrade Giyani Traffc Ligts and R81 lighting by 30 June 2019 | Upgrading Of Giyani Trafic Lights & R81 Lighting | Upgrading of streetlightd in R81 and Giyani CBD with the installation of New Traffic lights | R81 and Giyani CBD | Ward 11, 12 ,13 and 21 | LGES | 3500000 | 1'000'000 | Appoitment of Contractors | Installation of R81 Streetlights and 1 New Traffic light | N/A | N/A | N/A | N/A | N/A | N/A | Certificate of completion | TECH
Electricity Provision | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life | To Connect electricity for 454 units at Hlomela Siyandani & Babangu by June 2019 | 2236 Households connected | Coonection of 454 units at Hlomela Siyandani & Babangu by 30 June 2019 | Electrification of Hlomela Siyandani & Babangu Villages | Electrification of 454 units at Hlomela Siyandani&Babangu | Giyani | Ward 19, 7 and 3 | INEP | 400000 | 0'00 | Connect and energise 200 households. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Certificate of Completion | TECH
Dumping Site | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life? | To Rehabilitate Dumping Site by 30 June 2019 | Dumping Site Available | Approval of designs by Department of Water and Sanitation by 30 June 2019 | Dumping Site Development | Rehabilitation of Dumping Site | Giyani | Ward 21 | MIG | 4000000 | 1'000'000 | Approval of detailed designs | Site establishment | Construction | Advertisement of wastedisposal site and appointment of service provider | Target not achieved,Advertisement of wastedisposal site and appointment of service provider not done | Advertisement of wastedisposal site and appointment of service provider | Late approval of tender document | Tender document approval and bid specification committee to seat for advertisement | Designs, advert Appointment letter for service provider | TECH
Roads, Bridges and Storm water | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life? | Giyani Section E Upgrading From Gravel to tar Phase 2 by 30 June 2019 | New Indicator | Upgrading of 1.4Km road from gravel to tar at Giyani Section E Phase 2 by 30 June 2019 | Giyani Se ction E Upgrading From Gravel to tar Phase 2 | Upgrading 1.4 km km of road from gravel to tar | Giyani Section E | Ward 11 | MIG | 3000000 | 2000000 | N/A | N/A | advertisement of the project | appointment of service provider and Site establishment | Target achieved, appointment of service provider and Site establishment done | None | None | None | Advertisement of the project Appointement letter for the contractor acceptance letter | TECH
Roads, Bridges and Storm water | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life? | # of km road at Homu 14 B to 14 A tarred by 30 June 2019 | New Indicator | Construction of 4.3 Km road at Homu 14 B to 14 A by 30 June 2019 | Homu 14B to 14A uprgrading from gravel to tar | Upgrading of 4.3 km from Gravel to Tar | Homu 14B to 14A | Ward 9 | MIG | 9000000 | 8'404'498 | Construction | Construction | Construction | Completion | Target not achieved | Completion | Late appointment of surveyor to confirm the levels of the road. | Contracto to fastrack the progress on site for this project. | Progress report, Practical completion certificate | TECH
Roads, Bridges and Storm water | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life? | # of km road at Makosha to be paved by 30 June 2019 | New Indicator | Paving of 5,6 km at Makosha by 30 June 2019 | Makosha upgrading from gravel to paving | Upgrading of 5,6km from gravel to paving | Makosha | 14 | MIG | 9214739 | 28'995'349 | Construction | Construction | Construction | Completion | Target achieved,paving of 5,6km at Makosha done | None | None | None | progress reports and practical completion certificate | TECH
Roads, Bridges and Storm water | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life | To Upgrade 2.9 Km road from gravel to tar at Giyani Section F streets Phase 3 by 30 June 2019 | New Indicator | Upgrading of 2.9 Km road at Giyani Section F Streets from gravel to paving by 30 June 2019 | Upgrading of Giyani Section F Streets Phase 3 | Upgrading of 2.9 km Km from gravel to pave at Giyani Section Street Phase 3 | Giyani Section F | Ward 13 | MIG | 6444665 | 4'152'811 | N/A | Allocation of project to contactor | Construction | Completion | Target achieved, Upgrading of 2.9 Km road at Giyani Section F Streets from gravel to paving done | None | None | None | Practical completion certificate | TECH
Roads, Bridges and Storm water | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life? | # Km of roads to be paved at Bode by 30 June 2019 | New Indicator | Paving of 2.4 Km at Bode by 30 June 2019 | Bode paving of internal streets | Bode paving of 2.8km from gravel to paving blocks | Bode Village | Ward 7 | MIG | 2006623 | 7'944'420 | Completion | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Appointement letter, acceptance letter, Progress report, minutes, IA and practical completion. | TECH
Roads, Bridges and Storm water | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life? | To rehabilitate streets in Giyani by 30 June 2019 | Available streets | Rehabilitation of Giyani streets in all Sections by 30 June 2019 | Rehabilitation of streets in all sections | Pactching of potholes in streets in all section | Giyani | Ward 11, 12 ,13 and 21 | LGS | 1500000 | 0'00 | Pactching of potholes in streets in all section | Pactching of potholes in streets in all section | N/A | N/A | N/A | N/A | N/A | N/A | Progress Report | TECH
Roads, Bridges and Storm water | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life | To Upgrade Giyani Trafic Lights & R81 Lighting by 30 June 2019 | New Indicator | To Upgrade Of Giyani Trafic Lights & R81 Lighting by 30 June 2019 | Upgrading Of Giyani Trafic Lights & R81 Lighting | Upgrading Of Giyani Trafic Lights & R81 Lighting | Giyani CBD | Giyani | LGES | 3500000 | 1'000'000 | N/A | N/A | Upgrading Of R81 Lighting | Upgrading Of R81 Lighting | Target not achieved,Upgrading Of R81 Lighting not done | Upgrading Of R81 Lighting | Late appointment of contractor | GGM To appint a contractor . | Completion certificate | TECH
Roads, Bridges and Storm water | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life? | To rehabilitate Acess Roads To Tribal Offices by 30 June 2019 | Available streets | Rehabilitation of Acess Roads To Tribal Offices by 30 June 2019 | Rehabilitation of Acess Roads To Tribal Offices | Rehabilitation of Acess Roads To Tribal Offices | Blikwater, Hlaneki, Thomo, Makhuva, Nkomo, Nkuri, Dzumeri, Ngove | Ward 1,5,6,9,10,17,21,25 & 29 | LGES | 1000000 | 0 | Designs | Designs | N/A | N/A | N/A | N/A | N/A | N/A | Appointement letter, acceptance letter, Scoping report and preliminary design report | TECH
Roads, Bridges and Storm water | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life? | Alternative road to Giyani from R81 by 30 June 2019 | New Indicator | Scoping report and prelimiary designs | Alternative road to Giyani from R81 by 30 June 2019 | Alternative access road to Giyani from R81 via Ngove Village by 30 June 2019 | Giyani CBD | 21 | LGES | 5000000 | 1'500'000 | feasibility study | Feasibilty study | Designs | Designs | Target achieved,designs done | None | None | None | Scoping report and preliminary designs | TECH
Roads, Bridges and Storm water | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life? | Xikukwane gravel to tarr(RAL) (D3804 & D3805) by 30 June 2019 | New Indicator | Scoping report and prelimiary designs by 30 June 2019 | Xikukwane gravel to tar(RAL) (D3804 & D3805) | Xikukwane gravel to tar(RAL) (D3804 & D3805) | Xikukwane | 14 | LGES | 3000000 | 1'400'000 | feasibility study | Feasibilty study | Designs | Designs | Target achieved,designs done | None | None | None | Scoping report and preliminary designs | TECH
Roads, Bridges and Storm water | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life? | Upgrading of Road D3187 from gravel to tar by 30 June 2019 | New Indicator | Development of detailed designs by 30 June 2019 | Upgrading of Road D3187 from gravel to tar | Upgrading of Road D3187 from gravel to tar | Mageva To Makhuva | 25 - 29 | LGES | 1000000 | 0'00 | N/A | N/A | N/A | Designs | Target not achieved,designs not done | Designs | Road is implemented by RAL | Hand over of this project to be done to RAL | Scoping report | TECH
Roads, Bridges and Storm water | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life? | To upgrade Nkhensani Acces by 30 June 2019( Sidewalks, Lightining, Bus stop and stalls) by 30 June 2019 | New Indicator | Upgrading of Nkhensani Acess by 30 June 2019( Sidewalks, Lightining, Bus stop and stalls) | Upgrading of Nkhensani Access(sidewalks,,Lightning, ,Bus stop and ,stalls) | Upgrading of Nkhensani Acess( Sidewalks, Lightining, Bus stop and stalls) | Giyani Section A | Ward 12 | LGES | 1000000 | 0'00 | Designs | Designs | N/A | N/A | N/A | N/A | N/A | N/A | Appointement letter, acceptance letter, Scoping report | b
Road and Stormwater Infrastructure Maintenance | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life? | To patch potholes utelising asphalt at Municipal roads by 30 June 2019 | 20 sqm potholes patched | Patching of 4000m2 Potholes utelising asphalt at Greater Giyani access road by 30 June 2019 | Preventative maintenance of tarred roads in greater giyani municipality | To issue work orders to contractors,contractors to prepare the surface for patching and to patch utelising hot mix asphalt and complete works on site | Giyani Township | Ward 12,13,11,21 | LGES | 6 000 000 | 8'880'000 | 1000 square metres of potholes to be patched | 1000 square metres of potholes to be patched | 1000 square metres of potholes to be patched | 1000 square metres of potholes to be patched | Target achieved,1000 square metres of potholes patched | None | None | None | ,certification by ward councillors, | TECH.
Road and Stormwater Infrastructure Maintenance | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life | To develop of Roads and Storm water Master plan by 30 June 2019 | New Indicator | Development of Roads and stormwater master plan by 30 June 2019 | Road and Stormwater master plan | Data collection; roads and stormwater study; meeting with stakeholders; develop roads master plan | Giyani Township | All Wards | LGES | 1000000 | 500'000 | Completion | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Roads and stormwater master plan | TECH
Sports Facilities | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life | Refurbishment of Giyani Stadium and Section A Tennis Court by 30 June 2019 | New Indicator | Completion of refurbishment of Giyani A Tennis Court Stadium by 30 June 2019 | Refurbishment of Giyani Stadium and Section A Tennis Court | Refurbishment of section A Tennis courts, Boundry wall, Existing change rooms | Section A | 12 | MIG | 100000 | 0'00 | Construction | Construction | N/A | N/A | N/A | N/A | N/A | N/A | Completion certificate | TECH
Sports Facilities | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life | Development of designs for Section E sports Centre precint by 30 June 2019 | New Indicator | To develop designs for Section E sports centre precint (Road, sidewalks ,lightining) by 30 June 2019 | Section E sports Center Precint | Construction of a roof covering; athletic tracks; soccer pitch; parking area and side walks for section sports centre precinct | Giyani Township | Ward 11 | LGES | 2000000 | 0'00 | N/A | Designs | N/A | N/A | N/A | N/A | N/A | N/A | Scoping report, preliminary designs and detailed design report | TECH
Sports Facilities | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life? | To Construct Mageva sport centre by 30 June 2019 | New Indicator | Construction of Mageva sport centre by 30 June 2019 | Construction of Sports Center at Mageva | Construction of Sports Centre at Mageva | Mageva Village | Ward 24 | MIG | 10065240 | 4'000'000 | Construction | Construction | advertisement of the project | Appointment and site establishment | Target achieved,appointment and site establishment | None | None | None | advertisement of the project Appointement letter for the contractor acceptance letter and site handover certificate | TECH
Sports Facilities | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life? | To Refurbish Sporting Facility at Gawula by 30 June 2019 | New Indicator | To Refurbish Sporting Facility at Gawula by 30 June 2019 | Refurbshiment of Sporting Facility at Gawula | Refurbshiment of Sporting Facility at Gawula | Gawula Village | Ward 18 | MIG | 100000 | 0'00 | Construction | Construction | N/A | N/A | N/A | N/A | N/A | N/A |  | TECH
Sports Facilities | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life? | To Refurbish Shivulani Sports Center by 30 June 2019 | New Indicator | Refurbshiment of Shivulani Sports Center by 30 June 2019 | Refurbshiment of Shivulani Sports Center | Refurbshiment of Shivulani Sports Center | Shivulani Village | Ward 15 | MIG | 100000 | 0'00 | Completion | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Practical completion certificate. | TECH
Sports Facilities | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life? | To Refurbish Mavalani Indoor Sports Center by 30 June 2019 | New Indicator | Designs for Refurbshiment of Mavalani Indoor Sports Center by 30 June 2019 | Refurbshiment of Mavalani Indoor Sports Center | Refurbshiment of Mavalani Indoor Sports Center | Giyani Mavalani | Ward 20 | MIG | 500000 | 0'00 | Designs | Designs | N/A | N/A | N/A | N/A | N/A | N/A | Designs, | TECH
Sports Facilities | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life? | To conduct feasibility study for the development of Golf Course by 30 June 2019 | New Indicator | Feasibility studies by 30 June 2019 | Golf Course Development | To conduct feasibility study for the development of Golf Course | Section D1 | 11 | LGES | 250000 | 0'00 | Feasibilty study | Feasibilty study | N/A | N/A | N/A | N/A | N/A | N/A | Feasibility bstudy | TECH
| To develop sustainable infrastructure networks which promotes economic growth and improve quality of life? | To upgrade parking lot by 30 June 2019 | Available Parking lot | Upgrading of parking lot at Civic Centre & Brickyard By 30 June 2019 | Upgrading of packing lot | To upgrade the parking lot within the municipal offices | GGM offices | CBD | LGES | 1500000 | 0'00 | Designs | Designs | N/A | N/A | N/A | N/A | N/A | N/A | Designs | TECH
Municipal building | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life? | To refurbish Giyani Arts and Culture by 30 June 2019 | Arts and Culture Centre in place | Designs for Refurbishment of Giyani Arts and Culture by 30 June 2019 | Refurbishment of Giyani Arts & Culture Centre | To refurbish Giyani arts and arts culture and paving parking lot. | Giyani arts and culture centre | CBD | LGES | 1000000 | 0'00 | Designs | Designs | N/A | N/A | N/A | N/A | N/A | N/A | Designs | TECH
Municipal building | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life? | To install public transport shelters by 30 June 2019 | New Indicator | Designs for Installation of public transport shelters at CBD by 30 June 2019 | Public transport shelters | To install public transport shellter on public transport routes | All townships | CBD | LGES | 300000 | 0'00 | Designs | Designs | N/A | N/A | N/A | N/A | N/A | N/A | Designs | TECH
Municipal building | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life? | Commencement of construction for Ndhambi taxi rank by 30 June 2019 | New Indicator | Commencement of construction for Ndhambi taxi rank by 30 June 2019 | Ndhambi taxi rank | Construction of Ndhambi taxi rank | Ndhambi | Ward 25 | LGES | 1000000 | 0'00 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Appointement letter, acceptance letter, Progress report | TECH
Municipal building | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life? | To Appoint a consultant for construct Jim- Nghalalume community community hall by 30 June 2019 | New Indicator | Appointment of consultant for construction of Jim- Nghalalume community hall by 30 June 2019 | Jim-nghalalume community hall | Development detailed design for construction of community hall at Jim- Nghalalume community hall village | Jim- Nghalalume village | Ward 5 | LGES | 500000 | 0'00 | Designs | Designs | N/A | N/A | N/A | N/A | N/A | N/A | Designs | TECH
Municipal building | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life? | To Appoint a consultant for construction of N'wadzekudzeku community hall by 30 June 2019 | New Indicator | Appointment of consultan for construction of N'wadzekudzeku community hall by 30 June 2019 | N'wadzekudzeku community hall | Design Development of community N'wadzekudzeku village | N'wadzekudzeku | Ward 15 | LGES | 500000 | 0'00 | Designs | Designs | N/A | N/A | N/A | N/A | N/A | N/A | Designs | TECH
Municipal building | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life | To Appoint a Consultant for construction of erecting palisade fence at Muncipal Pound by 30 June 2019 | New Indicator | Appointment of Consultant for construction of erecting palisade fence at Municipal Pound by 30 June 2019 | extension of pallisade fence at pound station | Development detailed design fr construction of Pound Station Fencing | Dzingi-dzingi | Ward21 | LGES | 500000 | 0'00 | Designs | Designs | N/A | N/A | N/A | N/A | N/A | N/A | Designs | TECH
Municipal building Maintanance | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life? | To maintain all Municipal buildings by 30 June 2019 | Poor condition of municipaal buildings | Maintainance of municipal buildings and sports facilities by 30 June 2019 | Routine maintenance of Municipal buildings and sports centres as when required | Renovation of buildings, maintanance of water and sewer , replacement of doors , windows and painting | Giyani Township and Villages | Municipal Buildings | LGES | 2 424 954 | 1'000'000 | Maintainance of municipal buildings and sports facilities | Maintainance of municipal buildings and sports facilities | Maintainance of municipal buildings and sports facilities | Maintainance of municipal buildings and sports facilities | Target achieved,Maintainance of municipal buildings and sports facilities done | None | None | None | Copy of job cards signed by ward councellors and close up reports | TECH
Electricity Provision | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life?
Electricity Provision | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life?
Roads, Bridges and Storm water | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life?
Roads, Bridges and Stormwater | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life?
Roads, Bridges and Storm water | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life?
Roads, Bridges and Storm water | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life?
Roads, Bridges and Storm water | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life?
Roads, Bridges and Storm water | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life?
Roads, Bridges and Storm water | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life?
Roads, Bridges and Storm water | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life?
Sports Facilities | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life?
Sports Facilities | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life?
Sports Facilities | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life?
Building and Construction | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life?
Building and Construction | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life?
Building and Construction | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life?
Building and Construction | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life?
EPWP Infrastructure | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life? | # of people to be appointed through EPWP Social Program by 30 June 2019 | 169 | 150 People appointed through EPWP Social Program by 30 June 2019 | EPWP Social | Creation of jobs through EPWP Social Program | Giyani Township | All wards | EPWP | 4,364 000 | 5'000'000' | 150 People appointed through EPWP Social Program | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Signed Appointment Memo | TECH
EPWP Enviromental and Culture | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life? | # of people to be appointed through EPWP Enviromental and Culture Program by 30 June 2019 | 149 people appointed through EPWP Enviroment | 110 People appointed through EPWP Enviroment by 30 June 2019 | EPWP Enviromental and Culture | Creation of jobs through EPWP Enviromental and Culture Program | Giyani Township | All wards | EPWP | 3000000 |  | 110 People appointed through EPWP Enviromental and Culture | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Participant list, Payment Register,Attendance Register | COMM
Environmental Awareness Campaign | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life | # of environmental awareness to be conducted by 30 June 2019 | 8 awareness campaigns conducted | 8 x Awareness campaigns and Educational programs to be conducted by 30 June 2019 | Environmental Awareness Campaign | Conduction Education awareness campaigns on environmental management to communities | Greater Giyani | All wards | Income | 127790 |  | 2 Environmental Awareness Campaigns. | 2 Environmental Awareness Campaigns. | 2 Environmental Awareness Campaigns. | 2 Environmental Awareness Campaigns. | Target achieved: 2 awareness conducted | None | None | None | Progress Report., Attendance registers | COMM
Parks Maintenance | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life | # of Parks to be Maintained at Section A, B and C by 30 June 2019 | 3 Parks maintainned | Maintain 3 parks in Section A, B and E by the 30 June 2019 | Parks Maintenance | Maintanance of Parks at Greater Giyani | Section A, B and C | Ward 12 and 21 | Income | Operational | Operational | 3 parks to be maintained | 3 parks to be maintained | 3 parks to be maintained | 3 parks to be maintained | Target achieved: 14 scholar patrol conducted | 12 | To recover previous quarters shortfall | None | Progress Report., Attendance registers | COMM
Scholar Patrol | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life? | # of scholar patrol to be conducted by 30 June 2019 | 20 scholar patrols conducted | To conduct 20 scholar patrols by 30 June 2019 | Scholar Patrol | Conducting of Scholar patrols | All Wards | All Wards | Income | Operational | Operational | Conduct 5 scholar patrols | Conduct 5 scholar patrols | Conduct 5 scholar patrols | Conduct 5 scholar patrols | Target achieved: 14 scholar patrol conducted | 12 | To recover previous quarters shortfall | None | Reports | COMM
Speed Checks | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life? | # of speed checks conducted by 30 June 2019 | 20 speed checks conducted | To conduct 300 Speed checks by 30 June 2019 | Speed Checks | Conducting of Speed Checks | All Wards | All Wards | income | Operational | Operational | Conduct 5 Speed Checks | Conduct 5 Speed Checks | Conduct 150 Speed Checks | Conduct 140 Speed Checks | Target not achieved: 30 speed checks conducted | 110 | focussed on executing the higher number of warrantof arrests | Target over achieved the previous quarters | Reports | COMM
Warrant of arrests | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life | # Warrant arrest served by 30 June 2019 | 12 warrant of arrests served | 160 Warrant of arrests served by 30 June 2019 | Warrant of arrests | Serving warrant of arrests | All Wards | All Wards | income | Operational | Operational | Served 3 warrant of arrests | Served 3 warrant of arrests | Served 77 warrant of arrests | Served 77 warrant of arrests | Target not achieved: 28 warrents of arrest served | 25 | under staffing | 3 Traffic Officers posts advertised | Reports | COMM
Traffic summonses issued | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life | # of Traffic summons issued by 30 June 2019 | 7000 summonses issued | Issue 4400 summonses by 30 June 2019 | Traffic summonses issued | Isueing of traffic summonse | All Wards | All Wards | income | Operational | Operational | 583 traffic summonses issued | 584traffic summonses issued | 1616traffic summonses | 1617traffic summonses | Target achieve: 7191 summonses issued | 5574 | more defaulters on payment of summonses | None | Reports | COMM
Road safety Operations | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life | # of road blocks held by 30 June 2019 | 4 Road block operations held | 84 road blocks held by 30 June 2019 | Road blocks | Conducting of road blocks | All Wards | All Wards | income | Operational | Operational | Hold 3 K78 Road blocks | Hold 3 K78 Road blocks | Hold 39 Road blocks | Hold 39 Road blocks | Target not achieved15 road blocks conducted | 24 | focussed on executing the higher number of warrantof arrests | Target over achieved the previous quarters | Registers | COMM
Pound Station Operationalisation | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life | # of community safety awareness conducted by 30 June 2019 | 1 pound station operational | To conduct 4 community safety awarenesses by 30 June 2019 | Pound Station Operationalisation | Conduct community safety awarenesses and impounding of stray animals | All Wards | All Wards | income | Operational | Operational | 1 community safety awareness conducted | 1 community safety awareness conducted | 1 community safety awareness conducted | 1 community safety awareness conducted | Target achieved:1 community Safety awareness conducted during fourth quarter | None | None | None | Attendance registers | COMM
Payment of DLCA fees | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life | # of Payment of DLCA fees facilitated by 30 June 2019 | 12 payment of DLCA fees as per Government Gazette | 12 payment of DLCA fees facilitated by 30 June 2019 | Drivers Licence Card Agency | Facilitating payment of card agency | Giyani Section C | Ward 12 | Income | Operational | Operational | 3 payments | 3 payments | 3 payments | 3 payments | Target achieved:3 DLCA reports are submitted to BTO for payment | None | None | None | Reports | COMM
RTMS payments | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life | # of RTMS payments facilitated by by 30 June 2019 | 12 payments of RTMC fees as per SLA | 12 payments of RTMC fees facilitated by 30 June by 30 June 2019 | Road Traffic Management Corporation fees | Facilitating payment of RTMC fees | Giyani Section C | Ward 12 | Income | Operational | Operational | 3 payments | 3 payments | 3 payments | 3 payments | Target achieved:3 RTMC reports are submitted to BTO for payment | None | None | None | Reports | COMM
Calibration of VTS | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life | # of Calibration of VTS done by 30 June 2019 | 1calibration of VTS test equipment as per NRLA | 1calibration of VTS test equipment done by 30 June 2019 | Vehicle Testing Station Calibration | Facilitating calibration of VTS equipment | Giyani Section C | Ward 12 | Income | Operational | Operational | 1 Calibration of VTS | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Reports | COMM
Payment of SABS fees | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life | # Payment of SABS fees facilitated by 30 June 2019 | 2 payments of SABS FEES as per NRTA | 2 payments of SABS FEES facilitated by 30 June 2019 | SABS levy | Facilitating payment of SABS fees | Giyani Section C | Ward 12 | Income | Operational | Operational | 1 payment | N/A | 1 payment | N/A | Target not achieved: 3% SABS not paid | 1 | the SABS is failing to provide an accurate tax invoice | to prepare report after receiving tax invoice | Reports | COMM
Payment of Agency fees | To develop sustainable infrastructure networks which promotes economic growth and improve quality of life | # of Agency fees facilitated for payment by 30 June 2019 | 12 payment of Agency fee as SLA | 12 payment of Agency fee facilitated for payment by 30 June 2019 | 80% Agency fees | Facilitating payment of 80% egency | Giyani Section C | Ward 12 | Income | Operational | Operational | Facilitate 3 payments | Facilitate 3 payments | Facilitate 3 payments | Facilitate 3 payments | Target achieved: 3 Agency fees payment done | None | None | None | Reports | COMM
Note on A65: Khosa, MI (GGM): Delete this activity

## LLED
Priority Issue/Programme | Development Objective | Key Perfomance Indicator | Baseline | Annual Targets | Project Name | Project/Indicator Description | Location | Ward | Funding Source | Budget 2018/19 R'000 | Adjusted Budget R'000 | 1st Q Target | 2nd Q Targets | 3rd Q Targets | 4th Q Targets | 15/16 R'000 | Actual Performance | Variance | Reason for Variance | Corrective Measures | Portfolio Of Evidence | Dept
5.4. LOCAL ECONOMIC DEVELOPMENT (L0WER SDBIP)
Durban Indaba | To Create An Enabling Environment For Sustainable Economic Growth | # Of SMME to be exposed to Durban Indaba by 30 June 2019 | 1 SMME exposed to Durban indaba | 1 SMME to be exposed to Durban Indaba by 30 June 2019 | Durban Indaba | Organising and providing transport and accomodation to SMME to attend Durban Indaba | Giyani | Giyani | Income | 150 000 | 100'000 | N/A | N/A | N/A | Organising and providing transport and accomodation to SMME to attend Durban Indaba | operational | Target Achieved, 1 SMME exposed to Durban Indaba. Mr. Mabunda Rich representing Rixile Route attende the Inada | None | None | None | Invitation, attendance register | P & Dev
Female Entrepreneur of the year Awards | To Create An Enabling Environment For Sustainable Economic Growth | # of winners of the female entrepreneur of the year by 30 June 2019 | 3 female entrepreneur supported | 3 female entrepreneur supported by 30 June 2019 | Female Entrepreneur of the year Awards | Organizing event for female entrepreneur of the year | Giyani | Giyani | Income | 50 000 | 50'000 | Support of female entrepreneur Award | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Invitation. ,list of receipients

## LMFMV
Priority Issue/Programme | Development Objective | Key Perfomance Indicator | Baseline | Annual Targets | Project Name | Project Description | Location | Ward | Funding Source | Budget 2018/19 R'000 | Adjusted Budget R'000 | 1st Q Target | 2nd Q Targets | 3rd Q Targets | 4th Q Targets | 15/16 R'000 | Actual Performance | Variance | Reason for Variance | Corrective Measures | Portfolio Of Evidence | Dept
5.3. MUNICIPAL FINANCE MANAGEMENT AND VIABILITY (LOWER SDBIP)
Revenue Management | To improve financial management systems to enhance venue base | To review the revenue enhancement policies by 30 June 2019 | Revenue enhancement policies were reviewed | Revenue enhancement policies reviewed by 30 June 2019 | Revenue enhancement policies review | Send the policies for inputs by other department. Present the draft review to management. Submit to council for approval. | Greater Giyani Municipality | Administration | Income | Operational | Operational | N/A | N/A | Draft Reviewed Revenue enhancement policies (Rates, Tariff, Credit Control, Bad Debts) | Final Reviewed Revenue enhancement policies (Rates, Tariff, Credit Control, Debts Collection) | N/A | Target Achieved, Final Reviewed Revenue enhancement policies (Rates, Tariff, Credit Control, Debts Collection) | None | None | None | Draft/Final Policies (Rates Policy, Tariff Policy, Credit Control Policy, Debts Collection Policy) | B&T
Contract Management | To improve financial management systems to enhance venue base | To coordinate the signing of contracts and SLA by 30 June 2019 | Contracts and SLA were signed | Coordination of signing of contracts and SLA by 30 June 2019 | Contract Managemnt | Coordinate the signing of Contracts and SLA of appointed Service Providers | Greater Giyani Municipality | Administration | Income | Operational | Operational | N/A | N/A | All Appointed Service provider signed SLA's | All Appointed Service provider signed SLA's |  | Target Not Achieved, All Appointed Service provider did not sign SLA's on time, however they were all signed in July | None | SLA's were signed in July | None | Signed Contracts and signed SLA'S | B&T
Budget and Reporting | To improve financial management systems to enhance venue base | To table the draft budget to council by 31 March 2019 | Draft budget was tabled to council | Draft budget tabled to council by 31 March 2019 | Draft budget | Collect budget from departments, Consolidate the budget, Present the draft to management, Submit to council for approval | Greater Giyani Municipality | Administration | Income | Operational | Operational | N/A | N/A | Draft budget tabled to council | N/A | N/A | N/A | N/A | N/A | N/A | Draft budget and Council Resolution | B&T
Budget and Reporting | To improve financial management systems to enhance venue base | To submit the final budget to council by 31 May 2019 | Final budget was submitted to council | Final budget submitted to council by 31 May 2019 | Final budget | Take the draft budget for public participation with the IDP. Incorporate inputs and submit the budget for final approval | Greater Giyani Municipality | Administration | Income | Operational | Operational | N/A | N/A | N/A | Final budget | N/A | Target Achieved, Final Budget tabled to Council | None | None | None | Final budget and Council Resolution | B&T
Budget and Reporting | To improve financial management systems to enhance venue base | To submit the Financial statements submitted to AG by 31 August 2018 | Financial statements was compiled and submit to AG on the 31 August 2017 | Financial statements compiled and submit to AG by 31 August 2018 | Financial statements | Compile the financial statement. Review the compiled financial statement. Present to management meeting. Submit to AG for auditing. | Greater Giyani Municipality | Administration | Income | Operational | Operational | Financial statements compiled and submitted to AG | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Copy of Financial statements | B&T
Budget and Reporting | To improve financial management systems to enhance venue base | Number of section 71 reports submitted to Treasury within 10 days after the end of the month by 30 June 2019 | 12 Reports submitted in 2017/18 | 12 Section 71 Reports to be submitted to Treasury by 30 June 2019 | Section 71 report submission | Compile the section 71 report. Submit to treasury within 10 days after month end. Submit to council for approval. | Greater Giyani Municipality | Administration | Income | Operational | Operational | Submit 3 Section 71 reports | Submit 3 Section 71 reports | Submit 3 Section 71 reports | Submit 3 Section 71 reports | N/A | Target Achieved,3 Section 71 reports submitted to Treasury | None | None | None | Copy of acknowledgement of receipt by Treasuries | B&T
Supply Chain Management | To improve financial management systems to enhance venue base | # of tenders evaluated,adjudicated and appointed by 30 June 2019 | 45 tenders were evaluated,adjudicated and appointed | # of tenders evaluated, adjudicated and appointed by 30 June 2019 | Tender adjudication | Set date for adjudication committee. Adjudicate tenders within timeframe (90 days after closure of the tender). Write adjudication report to the Accounting Officer. | Greater Giyani Municipality | Administration | Income | Operational | Operational | # of tenders evaluated, adjudicated and appointed | # of tenders evaluated, adjudicated and appointed | # of tenders evaluated, adjudicated and appointed | # of tenders evaluated, adjudicated and appointed | N/A | Target Achieved,three tenders evaluated, Three adjudicated and Three appointed | None | None | None | Monthly Tender Reports | B&T
Supply Chain Management | To improve financial management systems to enhance venue base | # of quotations received and processed by 30 June 2019 | # of quotations processed# of quotations received) | # of quotations received and processed by 30 June 2019 | Quotations | Set date for quotation committee. Assess the quotation within timeframe (90 days after closure of the tender). Write adjudication report to the Accounting Officer. | Greater Giyani Municipality | Administration | Income | Operational | Operational | # of quotations received and processed | # of quotations received and processed | # of quotations received and processed | # of quotations received and processed | N/A | Target achieved, 67 of quotations received and processed | None | None | None | Quotations Report | B&T
Asset Management | To improve financial management systems to enhance venue base | To update a GRAP compliant Asset Register by 30 June 2019 | GRAP Compliant Asset Register was updated | GRAP Compliant Asset Register updated by 30 June 2019 | Asset Register | Receive new acquisitions, Bar code and capture into the asset register. Capture the expense of the project in progress. When the project is completed the unbundling and capitalisation into the asset register takes effect | Greater Giyani Municipality | Administration | Income | Operational | Operational | Receive new acquisition(movable assets), Bar code and capture into the asset register. | Receive new acquisition(movable assets), Bar code and capture into the asset register. | Receive new acquisition(movable assets), Bar code and capture into the asset register. | Receive new acquisition(movable assets), Bar code and capture into the asset register. | N/A | Target achieved, There were no new assset acquisitions in the fourth quarter | None | None | None | Asset Register | B&T

## LGGPP
Priority Issue/Programme | Development Objective | Key Perfomance Indicator | Baseline | Annual targets | Project Name | Project Description | Location | Ward | Funding Source | Budget 2018/19 R'000 | Adjusted Budget R'000 | 1st Q Target | 2nd Q Targets | 3rd Q Targets | 4th Q Targets | 15/16 R'000 | Actual Performance | Variance | Reason for Variance | Reason for Variance | Portfolio Of Evidence | Dept
5.5. GOOD GOVERNANCE AND PUBLIC PARTICIPATION (LOWER SDBIP)
Fraud and Anti - Corruption | To develop governance structures and systems that will ensure effective public consultation and organizational discipline | # of Fraud and Anti - Corruption cases reported and attended by 30 June 2019 | 2 cases reported | # of cases reported and attended by by 30 June 2019 | Fraud and Anti - Corruption | Investigate allegations of fraud and corruption | Greater Giyani Municipality | Admistration | Income | Operational | Operational | # of cases reported and attended | # of cases reported and attended | # of cases reported and attended | # of cases reported and attended | N/A | Target Achieved,no cases reported and attended to | None | None | None | Case Register | CORP
Public Participation | To develop governance structures and systems that will ensure effective public consultation and organizational discipline | # of ward committee meetings coordinated by 30 June 2019 | 372 Ward Committee meetings | 308 Ward Committee meetings coordinated by 30 June 2019 | Support services for monthly ward committee meetings | Support services through PPOs to have monthly ward committee meetings in each of 31 wards | Greater Giyani Municipality | Admistration | Income | Operational | Operational | Coordinate 31 ward committee meetings . | Coordinate 31 ward committee meetings . | Coordinate 123 ward committee meetings . | Coordinate 123 ward committee meetings . | 369,884 | Target not Achieved,only 31 ward committee meetings conducted | 92ward committee meetings | The Indicator was wrongly captured in the SDBIP, | The indicator will be corrected in the 2019/20 SDBIP | Attendance register, Ward committee quarterly report | CORP
Internal Auditing | To develop governance structures and systems that will ensure effective public consultation and organizational discipline | To develop the Internal Audit Charter, and Audit Committee Charter and submit to Audit Committee and council for approval by 30th June 2019 | 3 year Internal Audit plan and Internal Audit Charter, developed and submitted to Audit Committee for aproval by 30 June 2019 | 3 year Internal Audit plan and Internal Audit Charter, developed and submitted to Audit Committee for aproval by 30 June 2019 | Internal Audit plan and Audit Committee Charter | Internal Audit plan and Internal Audit Charter, developed and submitted to Audit Committee for aproval | Greater Giyani Municipality | Administration | Income | Operational | Operational | N/A | N/A | N/A | 3 year Internal Audit plan and Internal Audit Charter, developed and submitted to Audit Committee for aproval | Approved Internal Audit plan and Internal Audit Charter | Target not Achieved,3 year Internal Audit plan and Internal Audit Charter, developed and submitted to Audit Committee for aproval | 3 year Internal Audit plan and Internal Audit Charter, developed and submitted to Audit Committee for aproval | Audit Committee meeting was rescheduled | full adherence to Audit Committee schedule | MM | MM
Internal Auditing | To develop governance structures and systems that will ensure effective public consultation and organizational discipline | # of implementation of the Internal Audit Action Plan by 30th June 2019 | Implementation in 2017/18 Intenal Audit Action plan | # of implementation of the Internal Audit Action Plan by 30 June 2019 | Internal Audit Action Plan | Implementation of the Internal Audit Ation Plan | Greater Giyani Municipality | Admistration | Income | Operational | Operational | # of findings resolved in the Action Plan | # of findings resolved in the Action Plan | # of findings resolved in the Action Plan | # of findings resolved in the Action Plan | N/A | Target not Achieved,only 22 out of 59 were resolved | 37 outstanding |  |  | Updated Internal Audit Tracking register | MM
Internal Auditing | To develop governance structures and systems that will ensure effective public consultation and organizational discipline | # of implementation of the AG(SA) Action Plan by 30 June 2019 | Implementatiof AG(SA) Action Plan | Implementation of the AG(SA) action plan by 30 June 2019 | AG(SA) action plan | Implementation of the AG(SA) action plan | Greater Giyani Municipality | Admistration | Income | Operational | Operational | # of queries resolved in the Action Plan | # of queries resolved in the Action Plan | # of queries resolved in the Action Plan | # of queries resolved in the Action Plan |  | Target not Achieved,only 22 out of 59 were resolved | 38 outstanding | some of the findings can only be resolved during year end reporting | continuos follow up through AFS preparation meetings and Audit SteerCom | Updated Action plan | MM
Internal Auditing | To develop governance structures and systems that will ensure effective public consultation and organizational discipline | # of Audit and Performance Audit Committee meetings held by 30 June 2019 | 4 | 4 Audit and Performance Committte to be held by 30 June 2019 | Audit and Performance Audit Committee | Organize Audit and Performance Audit Committee meetings | Greater Giyani Municipality | Admistration | Income | Operational | Operational | 1 Audit and Performance Audit Committee | 1 Audit and Performance Audit Committee | 1 Audit and Performance Audit Committee | 1 Audit and Performance Audit Committee | N/A | Target Achieved, 1 Audit and Performance Audit Committee meeting conducted | None | None | None | Minutes, Attendance register, invitations | MM
Internal Auditing | To develop governance structures and systems that will ensure effective public consultation and organizational discipline | # of Audit and Performance Audit Committee Reports developed and submitted to Council by 30 June 2019 | 4 Audit and Performance Audit Committee Reports | 4 Audit and Performance Audit Committee Reports developed and submitted to Council by 30 June 2019 | Audit and Performance Audit Committee Reports | Develop Audit and Performance Audit Committee Reports | Greater Giyani Municipality | Admistration | Income | Operational | Operational | 1 Audit and Performance Audit Committee Reports | 1 Audit and Performance Audit Committee Reports | 1 Audit and Performance Audit Committee Reports | 1 Audit and Performance Audit Committee Reports | N/A | Target not Achieved,1 Audit and Performance Audit Committee Reports | 1 Audit and Performance Audit Committee Reports | Audit Committee meeting was rescheduled | full adherence to Audit Committee schedule | 4 Audit and Performance Audit Committee Reports and Council resolution | MM
Internal Auditing | To develop governance structures and systems that will ensure effective public consultation and organizational discipline | # of Audit Steering Committee meetings held by 30 June 2019 | 8Audit Steering Committee held | 8 Audit Steering Committee meetings held by 30 June 2019 | Audit Steering Committee | Organize Audit Steering Committee meetings | Greater Giyani Municipality | Admistration | Income | Operational | Operational | 2 Audit Steering Committee | 3 Audit Steering Committee | 1 Audit Steering Committee | 2 Audit Steering Committee | N/A | Target not Achieved, only 1 Steering committee meeting was conducted | 1 Audit Steering Committee | meeting was rescheduled | full adherence to Audit SteeringCommittee schedule | Minutes, Attendance register | MM
Performance Management | To develop governance structures and systems that will ensure effective public consultation and organizational discipline | # of organisational performance reports developed and submitted to Council by 30 June 2019 | 5 organisational performance reports developed | Develop 5 organisational performance reports and submit to Council by 30 June 2019 | Quarterly performance reports | Develop a reporting template and send to departments, Receive completed template and consolidate into one report. Organise SDBIP Management meeting to consider the report. Submit the report to Council for approval. | Greater Giyani Municipality | Admistration | Income | 100000 | 100000 | First Quarter SDBIP performance Report 2018/19 | Second Quarter SDBIP performance Report 2018/19 | Third Quarter SDBIP performance Report 2018/19 | Fourth Quarter SDBIP Performance Report 2017/18,Draft Annual Performance Report 2017/1 | Operational | Target Achieved,Fourth Quarter SDBIP Performance Report 2017/18,Draft Annual Performance Report 2017/1 | None | None | None | Quarterly reports | MM
Performance Management | To develop governance structures and systems that will ensure effective public consultation and organizational discipline | # of Section 54/56 Managers with signed performance agreements by 30 June 2019 | 5 signed performance agreements | # of Section 54/56 Managers with signed performance agreements by 30 June 2019 | Performance agreements | Develop draft performance agreements. Engage the relevant Section 54/56 Managers. Submit the final performance agreement to Municipal Manager for signing. Submit the signed agreement to MEC for Cooperative Governance Human Settlement and Traditional Affairs. | Greater Giyani Municipality | Admistration | Income | Operational | Operational | # of Secion 54/56 Managers signed Performance Agreements | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Signed Performance Agreements | MM
Promote community and environmental welfare | To develop governance structures and systems that will ensure effective public consultation and organizational discipline | To award 15 bursaries to qualifying learners by 30 June 2019 | 15 bursaries awarded | Bursaries to be awarded qualifying needy learners by 30 June 2019 | Bursaries | Awarding of bursaries to needy students | Greater Giyani Municipality | All wards | Income | 150000 |  | Advertisement for applicants to respond | Selection of the qualifiying students | Award 15 bursaries to qualifying applicants | N/A | N/A | N/A | N/A | N/A | N/A | Advert and Letters of bursary awards | CORP
Indigent Support | To develop governance structures and systems that will ensure effective public consultation and organizational discipline | # of qualifying households provided with indigent burial by 30 June 2019 | Indigent register in place | # of indigent burials provided by 30 June 2019 | Indigent Support | Conduct Assessment and offer indigent support to qualifying members of community as per the request for indigent support | Greater Giyani Municipality | All wards | Income | 50000 |  | # of indigent burials provided by 30 June 2019 | # of indigent burials provided by 30 June 2019 | # of indigent burials provided by 30 June 2019 | # of indigent burials provided by 30 June 2019 |  | Target not Achieved,No indigent burial request received | None | None | None | Assessment report. Implementation Report. | COMM
Library Outtreach Program | To develop governance structures and systems that will ensure effective public consultation and organizational discipline | # of library outreach conducted by 30 June 2019 | 12 Library outreach conducted | 16 Library outreach to be conducted by 30 June 2019 | Library outreach | conduct library outreach to identified schools | Greater Giyani Municipality | All wards | Income | 30000 |  | Conduct four(4) library outreach | Conduct four(4) library outreach | Conduct four(4) library outreach | Conduct four(4) library outreach |  | Target achieved: 4 library outreaches conducted | None | None | None | Attendence registers | COMM
Promote community and environmental welfare | To develop governance structures and systems that will ensure effective public consultation and organizational discipline | # of activities conducted on special programs by 30 June 2019(Mayor,s Tournament,Youth Support,Gender Support,HIV/Candle lighting,Child& Old Age Support, Disability Support, ) | 20 Special Programms activities conducted | 16 Special Programs organized by 30 June 2019 | Special Programs | Organize and conduct the special programs undertaken in the different desks of the Special Programs Unit | Greater Giyani Municipality | All wards | Income | 1 690 467 |  | 4 activities conducted | 4 activities conducted | 4 activities conducted | 2 activities conducted | Operational | Target Achieved, 5 activities conducted (Mayoral cup, Budget Speech, carrer exhibition and online application, old age golden games and Youth event at Vuhehli) | None | None | None | Attendance registers, programs | MM
Newsletter | To develop governance structures and systems that will ensure effective public consultation and organizational discipline | # of Rito newsletter procuded and circulated by 30 June 2019 | 4 Rito newsletter produced | 2 Rito newsletter edition to be produced and circulated by 30 June 2019 | Rito newsletter | Producing and Circulating of the Rito newsletter | Greater Giyani Municipality | Admistration | Income | 600000 | 600000 | 1 Rito newsletter edition to be procuced and circulated | N/A | N/A | 1 Rito newsletter edition to be procuced and circulated |  | Target not Achieved, 1 Rito newsletter edition not done | 1 Rito newsletter edition to be procuced and circulated | Service provider's contract expired and the tender was advertised | To appoint the service provider and procure Rito newsletter | 2 Rito newsletter editions | MM
Public Participation | To develop governance structures and systems that will ensure effective public consultation and organizational discipline | # of imbizos convened by 30 June 2019 | 4 Imbizos held | 4 imbizos convened by 30 June 2019 | Public Participation | Consult members of the public on service delivery issues | Greater Giyani Municipality | Admistration | Income | 500 000 | 500 000 | 1 Imbizo | 1 Imbizo | 1 Imbizo | 1 Imbizo |  | Target Achieved, 1 Imbizo conducted | None | None | None | Attendance register and Programme | MM
Public Participation | To develop governance structures and systems that will ensure effective public consultation and organizational discipline | # of ward reportback meetings coordinated by 30 June 2019 | 124 Report back meetings held | 124 ward report back meetings coordinated by 30 June 2019 | Ward Public Report Back meetings | Consult members of the public on service delivery issues | Greater Giyani Municipality | All wards | Income | Operational | Operational | 31 Ward reportback meetings coordinated | 31 Ward reportback meetings coordinated | 31 Ward reportback meetings coordinated | 31 Ward reportback meetings coordinated | N/A | Target Achieved,31 Ward reportback meetings coordinated | None | None | None | Attendance Registers and Minutes | CORP
Public Hearing of MPAC | To develop governance structures and systems that will ensure effective public consultation and organizational discipline | # of MPAC Public Hearing to be coordinated by 31 March 2019 | 1 MPAC Public hearing conducted on 31 March 2018 | 1 MPAC Public Hearing to be coordinated by 31 March 2019 | MPAC Public Hearing | Conduct public hearing of the 2016/17 Annual Report | Greater Giyani Municipality | Admistration | Income | Operational | Operational | N/A | N/A | Conduct MPAC public Hearing on 2016/17Annual Report | N/A | N/A | N/A | N/A | N/A | N/A | Attendance registers and Advert | CORP
Customer Satisfaction Survey | To develop governance structures and systems that will ensure effective public consultation and organizational discipline | To conduct Customer Satisfaction Survey by 30 June 2019 | 0 Customer satisfaction Survey conducted | 1 Customer satisfaction Survey conducted by 30 June 2019 | Customer Satisfaction Survey | Distribution of Customer Satisfaction survey quationaire to communities to collect information on customer satisfation | Greater Giyani Municipality | All wards | Income | Operational | Operational | Development of Customer Satisfaction Survey Forms and distribute to communities for completion and Compile a report | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Reports and Quationaires | MM
Disaster Response coordination | To develop governance structures and systems that will ensure effective public consultation and organizational discipline | # of national disaster recovery projects coordinated by 30 June 2019 | 3 Disaster Recovery Projects Cordinated | # of Disaster Recovery Projects Cordinated by 30 June 2019 | Disaster Recovery Projects | Coordination of national disaster projects | Greater Giyani Municipality | All wards | Income | 200000 |  | # of Disaster Recover Projects Cordinated | # of Disaster Recover Projects Cordinated | # of Disaster Recover Projects Cordinated | # of Disaster Recover Projects Cordinated |  | Target Achieved,13 Disaster incidents response coordinated | None | None | None | Reports | MM
Arts and Culture Support | To promote Arts and Culture within the community members | To host Arts and Culture Festival by September 2018 | 1 festival was held in 2017 | One event of Arts and Culture festival to be held in September 2018 | Arts & Culture Support | To host Arts and Culture festival | All Wards | All wards | Income | 200000 |  | 1 Arts and Culture festival held | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | purchase requisitions & attendence register | COMM
Heritage Day Celebration | To promote the Culture of heritage within members of the community | To host the celebration of Heritage Day Celebration by June 2019 | 1 heritage Day Celebration was held | 1 event of Heritage Day Celebration to be held in September 2019 | Heritage Day Celebration | To host Heritage Day Celebration | All Wards | All wards | Income | 45000 |  | Heritage Day Celebration held | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | purchase requisitions & attendence register | COMM
Sport Development | To develop Sports programmes within the community members | # of sporting code supported by June 2019 | 7 wards benefited | To support 1sporting code by June 2019 | Sport Development | To procure sporting equipments | All Wards | All wards | Income | 100000 |  | N/A | N/A | N/A | 1 sporting code supported | 2 sporting code supported | Target Achieved,3 sporting code supported | None | None | None | purchase requisitions and proof of payment | COMM
Indigenous games | To promote the Indigenous games within the community members | To Coordinate and host indigenous games within the community by 30 June 2019 | Local, District and Provincial Indigenous games coordinated and hosted | To coordinate the selection of local team of Indigenous by June 2019 | Indigenous Games | 1 local Indigenous games to be hosted | All Wards | All wards | Income | 50 ,000 |  | N/A | N/A | N/A | Local indigenous games selected conducted | 90000 | Target achieved: 1 Local indigenous games held | None | None | None | Purchase requisitions and attendence register | COMM
Note on K16: Rikhotso, M.J (GGM):

## APPROVAL
4th QUARTER SDBIP REPORT 2018/2019
Report Prepared By:
MAAKE KR
SENIOR PMS OFFICER
Report Reviwed By:
_____________________________________
RIKHOTSO MJ
MANAGER:PMS
Report approved by:
________________________________
CHAUKE M.M
MUNICIPAL MANAGER
DATE:

## WARD INFORMATION (hidden)
1. WARD INFORMATION FOR EXPENDITURE AND SERVICE DELIVERY
The budget breakdown per ward for 2017/18 is presented in the table below. This serves to collate service delivery information per ward for the benefit of ward councillors and their respective communities. Ideally ward councillors should receive separate quarterly reports showing progress on implementation of projects and service delivery targets in their wards.
Ward 1
Project name | Implementing agent | Settlement | Budget | Department
Ward 2
Project name | Implementing agent | Settlement | Budget | Department
Ward 3
Project name | Implementing agent | Settlement | Budget | Department
Nthuxi | GGM | Nthuxi |  | Technical
Ward 4
Project name | Implementing agent | Settlement | Budget | Department
Maswanganyi electrification | GGM | maswanganyi |  | Technical
Electrification of Nwamankena & Dingamazi Village( 450 units) | GGM | Nwamankena & Dingamazi |  | Technical
Ward 4
Project name | Implementing agent | Settlement | Budget | Department.
Ward 6
Project name | Implementing agent | Settlement | Budget | department
Elelectrification of Gandlanani village | GGM | Gandlanani | 400000 | Technical
Ward 7
Project name | Implementing agent | Settlement | Budget | Department
Paving of street bode | GGM | Bode | R3M | Technical
Ward 8
Project name | Implementing agent | Settlement | Budget | Department
Nwamankena
Ward 9
Project name | Implementing agent | Settlement | Budget | Department
Upgrading of road from gravel to tar homu 14b to homu 14 a | GGM | Homu 14a | R600,000 | Technical
Mapayeni culvert bridge | GGM | Mapayeni | R356,200 | Technical
Ward 10
Project name | Implementing agent | Settlement | Budget | Department
1nkomo b upgrading of road | GGM | Nkomo B | R10M | Technical
Nkomo b electrification | GGM | Nkomo B |  | Technical
Nkomo c electrification | GGM | Nkomo C |  | Technical
Ward 11
Project name | Implementing agent | Settlement | Budget | Department
Giyani section E sport center | GGM | Section E | 1 | Technical
Giyani section e Streets upgrading phase2 | GGM | Section E | R | Technical
Upgrading of Giyani golf estate | GGM | Section D1 | R0,2m | Technical
Ward 12
Project name | Implementing agent | Settlement | Budget | Department
1upgrading and lighting nkhensani road | GGM | Section A | R0,3m
2
3
Ward 13
Project name | Implementing agent | Settlement | Budget | Department
Technical
Giyani section f streets | GGM | Section F | R | Technical
Ward 14
Project name | Implementing agent | Settlement | Budget | Department
Formalization of xikukwani eco park | GGM | Xikukwani | R1m | Planning
Formalization of Risinga (makosha) | GGM | Makosha | R1m | Planning
Makosha upgrading of road | GGM | Makosha | R500,000 | Technical
Ward 15
Project name | Implementing agent | Settlement | Budget | Department
Ward 16
Project name | Implementing agent | Settlement | Budget | Department
Mninginisi electrification | GGM | Mninginisi | R1M | Technical
Mhlava willem electrification | GGM | Mhlava willem
Ward 17
Project name | Implementing agent | Settlement | Budget | Department
Thomo community hall | GGM | Thomo | R | Technical
Thomo community hall | GGM | Thomo | R | Technical
Ward 18
Project name | Implementing agent | Settlement | Budget | Department
Gawula electification | GGM | Gawula |  | technical
Ward 19
Project name | Implementing agent | Settlement | Budget | Department
Mahlathi electrification | GGM | Mahlathi |  | technical
technical
technical
Ward 20
Project name | Implementing agent | Settlement | Budget | Department
Mbatlo electrification | GGM | Mbatlo |  | Technical
Xivulani electrification | GGM | Xivulani |  | technical
Ward 21
Project name | Implementing agent | Settlement | Budget | Department
Waste disposal site | GGM | Ngobe | R10m | technical
Town expansion at ngobe | GGM | Ngobe | R0,3m | Planning
Dzingidzingi | GGM | Dzingidzingi | R | Technical
Ward 22
Project name | Implementing agent | Settlement | Budget | department
1shikhumbaelectrification | GGM | Shikhumba | R | Technical
Ward 23
Project name | Implementing agent | Settlement | Budget | Department
MUXIYANI |  |  |  | Technical
Kheyi |  |  |  | Technical
MUXIYANI |  |  |  | Technical
Ward 24
Project name | Implementing agent | Settlement | Budget | Department
Mageva sport center | GGM | Mageva | R6,5m | Technical
Bambeni electrification | Bambeni | bambeni | R1,5m | Technical
Mageva to makhuva road | GGM | Mageva to makhuva road | R1M | Technical
Ward 25
Project name | Implementing agent | Settlement | Budget | Department
Ndhambi taxi rank | GGM | Ndhambi | R3m | Technical
Technical
Technical
Ward 26
Project name | Implementing agent | Settlement | Budget | Department
Nkomo A upgrading of road | GGM | Nkomo A | R1M | Technical
Ward 27
Project name | Implementing agent | Settlement | Budget | Department
xitlakati | GGM | xitlakati
mzilela | GGM | Mzilela
Khaxani electrification | GGM | Khaxani
Ward 28
Project name | Implementing agent | Settlement | Budget | Department
Mbaula access road | GGM | Mbaula | R1m | Technical
Mbaula electrification | GGM | Mbaula
Ward 29
Project name | Implementing agent | Settlement | Budget | Department
Vuhehli electrification | GGM | Vuhehli |  | technical
Nwakhuwani electrification | GGM | Vuhehli |  | Technical
technical
Vuhehli electrification | GGM | Vuhehli |  | technical
Ward 30
Project name | Implementing agent | Settlement | Budget | Department